# ATTACHMENT A

# SCOPE OF WORK

Project Name: NCSD - Tonopah High School Sports Field Replacement

CORE Project No: 26-01-019

Subcontractor:

YESCO - Reno

800 B Bennie Lane
Reno, NV 89512

Phone: 775-284-8127

Contact Person: Karen Munson

Email: kmunson@yesco.com

# LUMP SUM PRICE FOR LABOR, MATERIAL, TAX, AND FREIGHT	     $99,483.00

# No Bond Included

Subcontractor has accounted for, as part of this lump sum Subcontract, any and all potential material, equipment, and labor cost increases over the course of the Project, unless otherwise noted in the Scope of Work.

SCOPE OF WORK:

- Subcontractor shall perform the Scope of Work generally described as:

Scoreboard

- Subcontractor shall provide a complete turnkey, (i.e., furnish and install), Scope of Work in accordance with Contract Documents to include, but not be limited to:

  - Subcontractor is required to supply Contractor with a material and equipment procurement log as it applies to Subcontractor’s Scope of Work.  Such material and equipment procurement log will show in detail the material product, date ordered, shipping date, and date of delivery to the Project site. Subcontractor shall provide documentation from each manufacturer and/or distributor confirming the dates shown on the procurement log.  Subcontractor agrees to update such procurement log and shall transmit either in hard copy or electronic format to the Contractor, on a bi-weekly basis, or more frequently as reasonably required by Contractor.

  - Subcontractor shall provide to Contractor cost flow projections monthly including computations and projections related to this Scope of Work. Projections shall include costs from and related to, manpower, coordination, supervision, equipment, and material for completing this Scope of Work.

  - Scoreboard - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Supply and install (1) Daktronics model FB-2021 single-sided football/track scoreboard, complete with all steel support structure, per Clarification #01, RFI #5.

    - Includes wireless scoring console controller with battery power option.

    - Provide all design and engineering for a complete, turnkey installation of the scoreboard structure and framing, including foundation design.

    - Structural foundation and framing design shown in the Bid Documents is for reference only.

    - Includes all deferred submittals, engineering, and permits required for the scoreboard structure.

    - Structural steel support components exposed to weather shall be hot-dip galvanized per the structural General Notes.

    - Employ a licensed electrician for all electrical work associated with the scoreboard equipment.

    - Complete final electrical connections and commissioning of the scoreboard.

    - Coordinate with Electrical Subcontractor to bring power within 10 feet of the scoreboard for final connections.

    - Coordinate with Electrical Subcontractor for load requirements of the transformer and enclosure mounted behind the scoreboard, per sheet note 3/E1-10.

    - Coordinate with Concrete Subcontractor for scoreboard foundation design, embed, and anchor bolt requirements.

    - Coordinate with Contractor for the location of underground piping affecting the scoreboard foundation.

    - Remove and legally dispose of all dirt spoils generated by this Scope of Work.

- Subcontractor has accounted for, as part of this lump sum Subcontract, the fact that the Contract Documents may not contain all required details, parts, or pieces necessary to provide a complete and functioning system.  Therefore, it is Subcontractor’s responsibility to make reasonably inferable assumptions and allowances, as part of its lump sum proposal, to help account for the design intent and ensure that all elements associated with the Scope of Work comply with all governing codes and regulations.

SCOPE OPTIONS:

- None.

CONSTRUCTION DOCUMENTS:

- Subcontractor shall adhere to all Project specifications within the Project Manual and all Project drawings as referenced in the Attachment C – Enumeration of Documents section of this Subcontract, specifically referencing the following:

- Provide all labor, material, equipment, and services required to furnish and install all items included in the division(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Division 00 – Procurement and Contracting Requirements

- Division 01 - General Requirements

- Provide all labor, material, equipment, and services required to furnish and install all items included in the section(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Section 11 68 43 - Football/Track Scoreboard

- All construction documents referenced in the Attachment C – Enumeration of Documents portion of this Subcontract can be downloaded from the following location:

- Procore – 5 – 26-01-019 - NCSD - Tonopah HS Sports Field Phs'd Replacement

- Invite to be sent to Project team

- Password: Subcontractor generated

Contractor will be using Procore web-based software on this Project to maintain an electronic set of As-Built Documents.  Subcontractor is to furnish electronically all As-Built documents, appropriate warranties and guarantee information, equipment manuals, operations, and maintenance manuals, all of which are a condition to achieving final completion and to receiving final payment.  A Project within Procore has been created for this Project and access will be given to Subcontractor.  All construction documents will be accessible to Subcontractor through Procore.  It will be the responsibility of Subcontractor to create As-Built documents electronically in the field in lieu of providing hard copies.  Contractor will provide training and support on Procore to Subcontractor.

To obtain access, Subcontractor must go to the Procore Software site (www.procore.com) and create a login.  Subcontractor shall create a Username and Password then send a corresponding email address to Contractor’s Project Manager; Contractor’s Project Manager will then email Subcontractor with an invitation to the Project in Procore.  Subcontractor may request additional instructions on how to create a login and Contractor’s Construction Technology department will provide assistance.

- Subcontractor shall adhere to all miscellaneous Project modifications, specifically referencing the following directives:

- Addendum #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #02 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

PROJECT SPECIFIC PROVISIONS:

- Subcontractor shall provide multiple mobilizations as required to complete the Scope of Work as per the dates set forth on the monthly baseline and weekly look-ahead schedules.

- Subcontractor’s foreman, at a minimum, shall attend all daily huddle, weekly work plan, and three phased QAQC plan meetings, which occur a reasonable time before and for the duration of the Subcontract Work on the Project.

- All Submittals shall be submitted in electronic format online using Procore.  Contractor may also request up to six (6) physical hard copies of all submittals.

- Subcontract pricing is based on tariff and/or duties rates in effect as of the date of this Subcontract.  If a net increase in tariffs and/or duties causes a net cost increase on materials, equipment, or products directly required to perform the Subcontract Work, the Subcontractor shall be entitled to a reasonable adjustment to the Subcontract Price to the extent the Prime Contract entitles Contractor to compensation for such increase and then only to the extent of any amount that Contractor may, on behalf of Subcontractor, recover from Owner.  To the extent applicable, any provisions regarding tariff changes in the Prime Contract shall flow down to this Subcontract. Subcontractor must supply reasonable documentation of proof of tariff and/or duties increase and cost impact between the date of this Subcontract and the date of said cost increase, based on an industry approved index associated with that of the affected material. Subcontractor must provide written notice of the cost impact and supporting documentation to Contractor within 7 calendar days of becoming aware. >Do Not Edit this paragraph you can delete all of it or keep all of it KH<

EXCLUSIONS:

- The following items are specifically excluded from the Subcontractor’s Scope of Work:

- Building permits

- Bonds

- Transformer and enclosure behind scoreboard

- Wired communication pathway to scoreboard

- Removal of existing scoreboard

- Scoreboard foundation excavation and concrete

DRAFT REVIEW ONLY - DELETE BEFORE ISSUE

This page is not part of the Subcontract and is not Scope of Work.

RULE 14 REVIEW - obligations removed from the Scope of Work above

Rule 14 keeps out of this exhibit anything the Contract Documents already state, so the Subcontract carries one copy of each obligation rather than two that can drift.

Every line below was drafted, verified and then removed on that basis. All of them still bind the Subcontractor through the document named beneath them. Tick any that should be restated in the Scope of Work above.

A.  Already stated in the Project Manual or on the Drawings

Restating these creates a second, weaker copy of the same obligation.

☐  Provide scoring console, electric operators, and operating hardware as specified and required.

already stated in: Section 11 6843 para 2.04 Scoring Console

☐  Provide all anchors, fasteners, and sealants required for a complete installation.

already stated in: Section 11 6843 Part 3 Installation; the turnkey clause already binding this Attachment A

☐  Provide final adjustments, start up, and training as specified.

already stated in: Section 11 6843 para 3.03 Installation - Control Center

☐  Include multiple mobilizations as may be required per the Preliminary Construction Schedule and Logistics Plan.

already stated in: this Attachment A, PROJECT SPECIFIC PROVISIONS (Mobilizations)

☐  Provide a competent foreman who shall participate in the daily huddle and weekly workplan meetings.

already stated in: this Attachment A, PROJECT SPECIFIC PROVISIONS

B.  Stated ONLY in a Scope of Work narrative

This is the one worth a decision. If the Scope of Work narrative is not an exhibit to the executed Subcontract, striking it removes the obligation outright rather than relocating it.

☐  Materials and installation shall comply with applicable ADA requirements.

already stated in: Scope of Work #089 only

No accessible route, control, or reach range is indicated for the scoreboard anywhere in the Contract Documents. May be boilerplate carried over from another package's narrative rather than a real obligation for this equipment type.

☐  Supply and install all footings, including excavation, backfill, compacted subbase, concrete, reinforcing, sleeves, anchors, and coring as required.

already stated in: Scope of Work #089 only

Struck to the exclusions list, not restated here as a duplicate -- Scope of Work #030 assigns this construction to the Concrete Subcontractor. Listed here because it is the clearest single line showing the two narratives conflict, and because YESCO's own priced 'Add alternate' for this exact scope is embedded in the carried Subcontract Amount. See the HIGHEST PRIORITY open PM item.

C.  Stated in no document at all

Trade means and methods. No document assigns this one; it is here only so the list is complete.

☐  Provide all rigging, cranes, and lifting equipment required to erect the scoreboard structure.

already stated in: Image360 and YESCO proposals each price a separate crane pick for this Scope of Work