# ATTACHMENT A

# SCOPE OF WORK

Project Name: NCSD - Tonopah High School Sports Field Replacement

CORE Project No: 26-01-019

Subcontractor:

Northstar Contracting Group, Inc.

5678 La Costa Canyon Court, Suite 105
Las Vegas, NV 89139

Phone: 702-220-4848

Contact Person: Fernando Cerda

Email: FCCerda@Northstar.com

# LUMP SUM PRICE FOR LABOR, MATERIAL, TAX, AND FREIGHT	     $741,912.00

# No Bond Included

Subcontractor has accounted for, as part of this lump sum Subcontract, any and all potential material, equipment, and labor cost increases over the course of the Project, unless otherwise noted in the Scope of Work.

SCOPE OF WORK:

- Subcontractor shall perform the Scope of Work generally described as:

Abatement & Building Wrecking

- Subcontractor shall provide a complete turnkey, (i.e., furnish and install), Scope of Work in accordance with Contract Documents to include, but not be limited to:

  - Subcontractor is required to supply Contractor with a material and equipment procurement log as it applies to Subcontractor’s Scope of Work.  Such material and equipment procurement log will show in detail the material product, date ordered, shipping date, and date of delivery to the Project site. Subcontractor shall provide documentation from each manufacturer and/or distributor confirming the dates shown on the procurement log.  Subcontractor agrees to update such procurement log and shall transmit either in hard copy or electronic format to the Contractor, on a bi-weekly basis, or more frequently as reasonably required by Contractor.

  - Subcontractor shall provide to Contractor cost flow projections monthly including computations and projections related to this Scope of Work. Projections shall include costs from and related to, manpower, coordination, supervision, equipment, and material for completing this Scope of Work.

  - Hazardous Material Remediation (Abandoned Elementary School) - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Remove and legally dispose of hazardous building materials at the abandoned elementary school (Idaho Circle), including all trucking and disposal fees.

    - Includes transportation and disposal of miscellaneous hazardous materials encountered during this Scope of Work.

    - Includes pre-abatement demolition of interior finishes, materials, equipment, and building components necessary to access hazardous materials, including off-haul and disposal to a legal landfill.

    - Includes stabilization of lead-based paint surfaces requiring removal.

    - Comply with the Pre-Demolition Asbestos Survey (dated October 3, 2023) and the Asbestos Management Plan for Nye County School District (dated January 4, 2022).

    - Provide, manage, maintain, and remove all containment, negative air pressurization, and HEPA filtration systems.

    - Limited to Buildings 3, 4, 5, 6 and 7; Buildings 1 and 2 remain occupied throughout this Scope of Work.

  - Building Wrecking (Abandoned Elementary School) - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Demolish and remove Buildings 3, 4, 5, 6 and 7 at the abandoned elementary school (Idaho Circle) as indicated, including all interior finishes, materials, equipment, and building system components.

    - Slabs-on-grade to remain; cut all reinforcing, anchor bolts, conduits, and piping flush with top of slab as indicated.

    - Cast-in-place concrete basement retaining wall at Building 4 to remain as indicated.

    - Includes removal of all plumbing, mechanical, and electrical equipment disconnected by others.

    - Demolish and remove existing wooden shed and floor structure at Building 4.

    - Cut and remove existing exterior wood posts at Building 5; remove and salvage existing exterior steel canopy posts, coordinating with Contractor for protection, storage, and re-installation by others.

    - Demolish and remove exterior walkway canopies as indicated.

    - Includes all sawcutting necessary to complete this Scope of Work.

    - Cut and cap water and sewer lines a minimum 24 inches below finish slab as indicated.

  - Site Clearing (Abandoned Elementary School Campus) - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Sawcut and remove all concrete paving, steps-on-grade, and equipment pads as indicated.

    - Remove trees, including stump grinding, as indicated.

    - Demolish and remove landscaping, including shut-off of irrigation, sprinklers, and the main water line as indicated.

    - Remove and dispose of existing chain link fencing and gates, handrails, playground equipment, and basketball hoops and posts, including all footings.

    - Fill open stem wall CMU cells with dirt as indicated, per 1/AD1.15.

    - Provide rough site grading at completion, including backfilling footing holes and excavated trenches with native materials.

    - Remove and haul off existing propane tank and associated piping.

    - Coordinate with Electrical Subcontractor for safe-off of feeders from the transformer to the demolished buildings; remove, haul, and dispose of feeders outside building footprints.

    - Cap abandoned water line as required.

    - Provide traffic control plans, flagging, and barricades for offsite activities required for this Scope of Work only; obtain required offsite excavation and traffic control permits.

    - Provide dust palliative as indicated at completion of work at this site.

  - General Scope Requirements

    - Includes all provisions for confined space work as may be required.

    - Provide dust control for all operations per Nye County Air Quality requirements.

    - Clean and maintain trucking access routes, including street sweeping, for this Scope of Work only.

    - Coordinate with Utility, Plumbing, Mechanical, and Electrical Subcontractors to ensure utilities are capped and made safe prior to demolition within the building envelope.

- Subcontractor has accounted for, as part of this lump sum Subcontract, the fact that the Contract Documents may not contain all required details, parts, or pieces necessary to provide a complete and functioning system.  Therefore, it is Subcontractor’s responsibility to make reasonably inferable assumptions and allowances, as part of its lump sum proposal, to help account for the design intent and ensure that all elements associated with the Scope of Work comply with all governing codes and regulations.

SCOPE OPTIONS:

- None.

CONSTRUCTION DOCUMENTS:

- Subcontractor shall adhere to all Project specifications within the Project Manual and all Project drawings as referenced in the Attachment C – Enumeration of Documents section of this Subcontract, specifically referencing the following:

- Provide all labor, material, equipment, and services required to furnish and install all items included in the division(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Division 00 – Procurement and Contracting Requirements

- Division 01 - General Requirements

- Provide all labor, material, equipment, and services required to furnish and install all items included in the section(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Section 02 41 00 - Demolition

- All construction documents referenced in the Attachment C – Enumeration of Documents portion of this Subcontract can be downloaded from the following location:

- Procore – 5 – 26-01-019 - NCSD - Tonopah HS Sports Field Phs'd Replacement

- Invite to be sent to Project team

- Password: Subcontractor generated

Contractor will be using Procore web-based software on this Project to maintain an electronic set of As-Built Documents.  Subcontractor is to furnish electronically all As-Built documents, appropriate warranties and guarantee information, equipment manuals, operations, and maintenance manuals, all of which are a condition to achieving final completion and to receiving final payment.  A Project within Procore has been created for this Project and access will be given to Subcontractor.  All construction documents will be accessible to Subcontractor through Procore.  It will be the responsibility of Subcontractor to create As-Built documents electronically in the field in lieu of providing hard copies.  Contractor will provide training and support on Procore to Subcontractor.

To obtain access, Subcontractor must go to the Procore Software site (www.procore.com) and create a login.  Subcontractor shall create a Username and Password then send a corresponding email address to Contractor’s Project Manager; Contractor’s Project Manager will then email Subcontractor with an invitation to the Project in Procore.  Subcontractor may request additional instructions on how to create a login and Contractor’s Construction Technology department will provide assistance.

- Subcontractor shall adhere to all miscellaneous Project modifications, specifically referencing the following directives:

- Addendum #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #02 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

PROJECT SPECIFIC PROVISIONS:

- Subcontractor shall provide multiple mobilizations as required to complete the Scope of Work as per the dates set forth on the monthly baseline and weekly look-ahead schedules.

- Subcontractor’s foreman, at a minimum, shall attend all daily huddle, weekly work plan, and three phased QAQC plan meetings, which occur a reasonable time before and for the duration of the Subcontract Work on the Project.

- All Submittals shall be submitted in electronic format online using Procore.  Contractor may also request up to six (6) physical hard copies of all submittals.

- Subcontract pricing is based on tariff and/or duties rates in effect as of the date of this Subcontract.  If a net increase in tariffs and/or duties causes a net cost increase on materials, equipment, or products directly required to perform the Subcontract Work, the Subcontractor shall be entitled to a reasonable adjustment to the Subcontract Price to the extent the Prime Contract entitles Contractor to compensation for such increase and then only to the extent of any amount that Contractor may, on behalf of Subcontractor, recover from Owner.  To the extent applicable, any provisions regarding tariff changes in the Prime Contract shall flow down to this Subcontract. Subcontractor must supply reasonable documentation of proof of tariff and/or duties increase and cost impact between the date of this Subcontract and the date of said cost increase, based on an industry approved index associated with that of the affected material. Subcontractor must provide written notice of the cost impact and supporting documentation to Contractor within 7 calendar days of becoming aware. >Do Not Edit this paragraph you can delete all of it or keep all of it KH<

EXCLUSIONS:

- The following items are specifically excluded from the Subcontractor’s Scope of Work:

- Building permits

- Bonds

- Abatement or demolition of Buildings 1 and 2

- Underground utility demolition and relocation outside building footprints

- Building 4 lower-level stem wall demolition, AD1.16 alternate

DRAFT REVIEW ONLY - DELETE BEFORE ISSUE

This page is not part of the Subcontract and is not Scope of Work.

RULE 14 REVIEW - obligations removed from the Scope of Work above

Rule 14 keeps out of this exhibit anything the Contract Documents already state, so the Subcontract carries one copy of each obligation rather than two that can drift.

Every line below was drafted, verified and then removed on that basis. All of them still bind the Subcontractor through the document named beneath them. Tick any that should be restated in the Scope of Work above.

A.  Already stated in the Project Manual or on the Drawings

Restating these creates a second, weaker copy of the same obligation.

☐  Obtain required demolition permits from the Authority Having Jurisdiction.

already stated in: Section 02 41 00 para 3.02.A.1

☐  Comply with all applicable AHJ and OSHA requirements for this Scope of Work.

already stated in: general Subcontract Agreement terms; standard code compliance

☐  Provide, erect, and maintain temporary barriers and security devices to prevent access to hazardous areas.

already stated in: Section 02 41 00 paras 3.02.A.3-4

☐  Protect existing structures to remain from damage; conduct demolition to minimize the development and spread of dust.

already stated in: Section 02 41 00 para 3.02.C; Sheet AD1.11 Demolition Notes 4-5

☐  Field verify existing conditions prior to the start of demolition operations; report discrepancies to the Architect.

already stated in: Section 02 41 00 para 3.04.A.1-2; Sheet AD1.11 Demolition Note 3

☐  Maintain means of egress separate from construction areas at all times; ensure safe passage around demolition areas.

already stated in: Sheet AD1.11 Demolition Notes 8-9

☐  Clean adjacent structures and improvements of dust, dirt, and debris caused by demolition operations.

already stated in: Sheet AD1.11 Demolition Note 9

☐  Coordinate work with utility companies; protect existing utilities to remain from damage; do not disrupt utilities without required notice.

already stated in: Section 02 41 00 paras 3.03.A-E

☐  Immediately cease work and notify Architect and Owner if hazardous materials are discovered during removal operations.

already stated in: Section 02 41 00 para 3.02.D

☐  Remove exposed piping, valves, meters, equipment, supports, and foundations of disconnected and abandoned utilities.

already stated in: Section 02 41 00 paras 3.01.M, 3.03.G

☐  Coordinate with Contractor for removal, protection, and storage of items to be returned, re-used, or re-installed.

already stated in: Section 02 41 00 paras 1.03.C-D, 3.01.M

☐  Provide all necessary protection of adjacent finishes and surfaces at the perimeter of demolition areas.

already stated in: Section 02 41 00 para 3.02.C; general Subcontract Agreement terms

☐  Provide all trash dumpsters required for this Scope of Work.

already stated in: Section 02 41 00 para 3.05.A

☐  Haul off and legally dispose of all waste generated by this Scope of Work.

already stated in: Section 02 41 00 paras 3.05.A-B

☐  Remove debris, junk, and trash from the site; leave the site in a clean condition ready for subsequent work.

already stated in: Section 02 41 00 paras 3.05.A, 3.05.C

B.  Stated ONLY in a Scope of Work narrative

These are the ones worth a decision. If the Scope of Work narrative is not an exhibit to the executed Subcontract, striking these removes the obligation outright rather than relocating it.

☐  Coordinate with Contractor to ensure demolition areas have been cleared by the Hazardous Materials Remediation Subcontractor prior to the start of work.

already stated in: Scope of Work #002 only

Moot as drafted - this Subcontractor performs both the abatement and building wrecking scopes under this single package, so there is no separate remediation subcontractor to clear the area.