# ATTACHMENT A

# SCOPE OF WORK

Project Name: NCSD - Tonopah High School Sports Field Replacement

CORE Project No: 26-01-019

Subcontractor:

CG&B Enterprises, Inc.

2250 Corporate Circle, Suite 320
Henderson, NV 89074

Phone: 702-565-6564

Contact Person: Craig Edwards

Email: c.edwards@cgandbinc.com

# LUMP SUM PRICE FOR LABOR, MATERIAL, TAX, AND FREIGHT	     $1,139,000.00

# No Bond Included

Subcontractor has accounted for, as part of this lump sum Subcontract, any and all potential material, equipment, and labor cost increases over the course of the Project, unless otherwise noted in the Scope of Work.

SCOPE OF WORK:

- Subcontractor shall perform the Scope of Work generally described as:

Synthetic Turf Sports Field

- Subcontractor shall provide a complete turnkey, (i.e., furnish and install), Scope of Work in accordance with Contract Documents to include, but not be limited to:

  - Subcontractor is required to supply Contractor with a material and equipment procurement log as it applies to Subcontractor’s Scope of Work.  Such material and equipment procurement log will show in detail the material product, date ordered, shipping date, and date of delivery to the Project site. Subcontractor shall provide documentation from each manufacturer and/or distributor confirming the dates shown on the procurement log.  Subcontractor agrees to update such procurement log and shall transmit either in hard copy or electronic format to the Contractor, on a bi-weekly basis, or more frequently as reasonably required by Contractor.

  - Subcontractor shall provide to Contractor cost flow projections monthly including computations and projections related to this Scope of Work. Projections shall include costs from and related to, manpower, coordination, supervision, equipment, and material for completing this Scope of Work.

  - Synthetic Turf Sports Field - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Supply and install a complete NFHS-compliant synthetic turf system, including base, geotextile, shock pad, header boards, turf, and infill.

    - Basis of design is Hellas Matrix Helix 46 oz. turf, Elia Renufill/Realfill infill, and Soteria 20mm shock pad.

    - Includes fine grading of the aggregate base to manufacturer tolerance for turf installation.

    - Supply and install approximately 1,134 linear feet of nailer board on concrete curb supplied by others.

    - Includes turf colors as indicated (RS-101, RS-102, RS-103).

    - Includes football and soccer game striping, lettering, and center field logo, as indicated.

    - Perform percolation testing prior to installation.

    - Provide HIC and G-Max testing upon completion, including additional mobilizations as required.

    - Coordinate with Landscaping, Running Track Surfacing, Concrete, and Wet Utilities Subcontractors as required.

    - Provide dust control per Nye County Air Quality requirements for this Scope of Work.

    - Clean and maintain trucking access routes, including street sweeping, for this Scope of Work only.

    - Legally dispose of all soil spoils and debris generated by this Scope of Work; no stockpiling permitted.

- Subcontractor has accounted for, as part of this lump sum Subcontract, the fact that the Contract Documents may not contain all required details, parts, or pieces necessary to provide a complete and functioning system.  Therefore, it is Subcontractor’s responsibility to make reasonably inferable assumptions and allowances, as part of its lump sum proposal, to help account for the design intent and ensure that all elements associated with the Scope of Work comply with all governing codes and regulations.

SCOPE OPTIONS:

- None.

CONSTRUCTION DOCUMENTS:

- Subcontractor shall adhere to all Project specifications within the Project Manual and all Project drawings as referenced in the Attachment C – Enumeration of Documents section of this Subcontract, specifically referencing the following:

- Provide all labor, material, equipment, and services required to furnish and install all items included in the division(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Division 00 – Procurement and Contracting Requirements

- Division 01 - General Requirements

- Provide all labor, material, equipment, and services required to furnish and install all items included in the section(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Section 32 18 13 - Synthetic Turf

- All construction documents referenced in the Attachment C – Enumeration of Documents portion of this Subcontract can be downloaded from the following location:

- Procore – 5 – 26-01-019 - NCSD - Tonopah HS Sports Field Phs'd Replacement

- Invite to be sent to Project team

- Password: Subcontractor generated

Contractor will be using Procore web-based software on this Project to maintain an electronic set of As-Built Documents.  Subcontractor is to furnish electronically all As-Built documents, appropriate warranties and guarantee information, equipment manuals, operations, and maintenance manuals, all of which are a condition to achieving final completion and to receiving final payment.  A Project within Procore has been created for this Project and access will be given to Subcontractor.  All construction documents will be accessible to Subcontractor through Procore.  It will be the responsibility of Subcontractor to create As-Built documents electronically in the field in lieu of providing hard copies.  Contractor will provide training and support on Procore to Subcontractor.

To obtain access, Subcontractor must go to the Procore Software site (www.procore.com) and create a login.  Subcontractor shall create a Username and Password then send a corresponding email address to Contractor’s Project Manager; Contractor’s Project Manager will then email Subcontractor with an invitation to the Project in Procore.  Subcontractor may request additional instructions on how to create a login and Contractor’s Construction Technology department will provide assistance.

- Subcontractor shall adhere to all miscellaneous Project modifications, specifically referencing the following directives:

- Addendum #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #02 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

PROJECT SPECIFIC PROVISIONS:

- Subcontractor shall provide multiple mobilizations as required to complete the Scope of Work as per the dates set forth on the monthly baseline and weekly look-ahead schedules.

- Subcontractor’s foreman, at a minimum, shall attend all daily huddle, weekly work plan, and three phased QAQC plan meetings, which occur a reasonable time before and for the duration of the Subcontract Work on the Project.

- All Submittals shall be submitted in electronic format online using Procore.  Contractor may also request up to six (6) physical hard copies of all submittals.

- Subcontract pricing is based on tariff and/or duties rates in effect as of the date of this Subcontract.  If a net increase in tariffs and/or duties causes a net cost increase on materials, equipment, or products directly required to perform the Subcontract Work, the Subcontractor shall be entitled to a reasonable adjustment to the Subcontract Price to the extent the Prime Contract entitles Contractor to compensation for such increase and then only to the extent of any amount that Contractor may, on behalf of Subcontractor, recover from Owner.  To the extent applicable, any provisions regarding tariff changes in the Prime Contract shall flow down to this Subcontract. Subcontractor must supply reasonable documentation of proof of tariff and/or duties increase and cost impact between the date of this Subcontract and the date of said cost increase, based on an industry approved index associated with that of the affected material. Subcontractor must provide written notice of the cost impact and supporting documentation to Contractor within 7 calendar days of becoming aware. >Do Not Edit this paragraph you can delete all of it or keep all of it KH<

EXCLUSIONS:

- The following items are specifically excluded from the Subcontractor’s Scope of Work:

- Building permits

- Bonds

- Subgrade preparation

- Concrete curb and track perimeter drainage

- Running track surfacing

- Athletic field equipment and event surfacing

- Field drainage system inside turf perimeter

DRAFT REVIEW ONLY - DELETE BEFORE ISSUE

This page is not part of the Subcontract and is not Scope of Work.

RULE 14 REVIEW - obligations removed from the Scope of Work above

Rule 14 keeps out of this exhibit anything the Contract Documents already state, so the Subcontract carries one copy of each obligation rather than two that can drift.

Every line below was drafted, verified and then removed on that basis. All of them still bind the Subcontractor through the document named beneath them. Tick any that should be restated in the Scope of Work above.

A.  Already stated in the Project Manual or on the Drawings

Restating these creates a second, weaker copy of the same obligation.

☐  Supply a turf groomer to the Owner, with towing mechanism and instructions, as specified.

already stated in: Section 32 18 13 para 2.3

☐  Provide extra turf, pad and infill materials to the Owner upon completion.

already stated in: Section 32 18 13 para 1.11

☐  Provide all tests and certifications required for a complete and operational system.

already stated in: Section 32 18 13 para 1.4.C; general Division 01 requirements

☐  Provide a qualified manufacturer's representative onsite for all tests and inspections.

already stated in: Section 32 18 13 paras 1.5.C, 1.5.D

☐  Provide certifications from manufacturers and governing authorities as required.

already stated in: Section 32 18 13 paras 1.4.H, 1.8

☐  Receive, offload and store all products under cover, elevated above grade.

already stated in: Section 32 18 13 para 1.7

☐  Include multiple mobilizations as may be required per the Preliminary Construction Schedule and Logistics Plan.

already stated in: this Attachment A, PROJECT SPECIFIC PROVISIONS paragraph 94

Conflict - CG&B's proposal prices only one mobilization and charges $6,500 for each additional. See open PM item 022-02.

B.  Stated ONLY in a Scope of Work narrative

These are the ones worth a decision. If the Scope of Work narrative is not an exhibit to the executed Subcontract, striking these removes the obligation outright rather than relocating it.

☐  Subcontractor is responsible for scheduling testing and walking with inspectors to obtain sign-off of all systems for final approval.

already stated in: Scope of Work #022 only

☐  Provide an on-site representative at the time of delivery to confirm condition and receipt of all products and equipment.

already stated in: Scope of Work #022 only

C.  Stated in no document at all

Trade means and methods. No item of this kind surfaced for this package.