# ATTACHMENT A

# SCOPE OF WORK

Project Name: NCSD - Tonopah High School Sports Field Replacement

CORE Project No: 26-01-019

Subcontractor:

Sahara Concrete, Inc.

989 Empire Mesa Way, Suite C
Henderson, NV 89011

Phone: 702-798-7101

Contact Person: Danny Clayton

Email: dclayton@saharaconcrete.com

# LUMP SUM PRICE FOR LABOR, MATERIAL, TAX, AND FREIGHT	     $1,278,459.84

# No Bond Included

Subcontractor has accounted for, as part of this lump sum Subcontract, any and all potential material, equipment, and labor cost increases over the course of the Project, unless otherwise noted in the Scope of Work.

SCOPE OF WORK:

- Subcontractor shall perform the Scope of Work generally described as:

Concrete

- Subcontractor shall provide a complete turnkey, (i.e., furnish and install), Scope of Work in accordance with Contract Documents to include, but not be limited to:

  - Subcontractor is required to supply Contractor with a material and equipment procurement log as it applies to Subcontractor’s Scope of Work.  Such material and equipment procurement log will show in detail the material product, date ordered, shipping date, and date of delivery to the Project site. Subcontractor shall provide documentation from each manufacturer and/or distributor confirming the dates shown on the procurement log.  Subcontractor agrees to update such procurement log and shall transmit either in hard copy or electronic format to the Contractor, on a bi-weekly basis, or more frequently as reasonably required by Contractor.

  - Subcontractor shall provide to Contractor cost flow projections monthly including computations and projections related to this Scope of Work. Projections shall include costs from and related to, manpower, coordination, supervision, equipment, and material for completing this Scope of Work.

  - Site Concrete - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Supply and place concrete flatwork, curbs, take-off boards, athletic equipment pads, and turndown edges as indicated, including all layout.

    - Supply and install concrete curbs at the Synthetic Turf Sports Field and Running Track, and concrete equipment pads including the transformer pad.

    - Supply and install the slot drain / trench drain and concrete curb system along the track perimeter per detail D/L1.03, including excavation, trenching, bedding, backfill, piping, collector pipe, cleanouts, and drainage structures for a complete system. Connection to the site storm drainage system by others.

    - Provide cast-in-place footings for the Scoreboard, Press Box, Prefabricated Ticket Booth (slab-on-grade and footings), Bleacher footings/grade beams, and Track & Field Athletic Equipment (goal posts, high jump posts, etc.) as indicated, including excavation, backfill and overexcavation per the Geotechnical Report. Coordinate requirements with each respective equipment Subcontractor.

    - Bleacher footings are based on the manufacturer's foundation design, in lieu of the foundation shown on the structural drawings.

    - Excavate drilled piers and place concrete backfill around the Musco-furnished precast bases at sports field light poles, per E0-05. Coordinate pole locations and conduit interface with Electrical Subcontractor.

    - Install steel embeds, base plates and anchor bolts supplied by others; provide dry pack and non-shrink grout at base plates as indicated.

    - Install bollards supplied by others; provide concrete footings, infill, and domed tops.

    - Supply and place Type II aggregate base beneath this Scope of Work's flatwork, curbs and pads, on subgrade prepared and compacted by others.

    - Includes footing and installation for one flagpole, flagpole supplied by others.

  - Cast-in-Place Structural Concrete - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Supply and install continuous footings, slab-on-grade, and turned-down edges at the Concessions Building, including all layout.

    - Provide concrete housekeeping and equipment pads, including curbs, at the Concessions Building as indicated on the MEP drawings.

    - Provide concrete pour backs at floor sinks and restroom slope-to-drain locations.

    - Provide stepped footings at utility entrances; assume a 3-foot step.

    - Excavate, backfill and compact building wall and isolated footings with approved fill material.

    - Furnish and install Type II and vapor/moisture barrier at slabs-on-grade per the Geotechnical Report, installed after other trades complete underground rough-in.

    - Supply and install damproofing / waterproofing at footings and foundations.

    - Demonstrate joint and finish conditions on a 15'x15' mockup slab on-site; coordinate location and requirements with the onsite Superintendent.

  - General Scope Requirements

    - Provide layout from Contractor-furnished hubs, including gridline back-checking and batter boards for use by other trades.

    - Coordinate with Wet Utilities, Plumbing, HVAC, and Electrical & Low Voltage Subcontractors for fixtures, conduits, and sleeves in slab-on-grade.

    - Coordinate masonry rebar laps with Masonry Subcontractor; rebar lap to start at Finish Floor unless directed otherwise.

    - Supply, install and maintain rebar safety caps until Masonry Subcontractor assumes responsibility.

    - Supply and place all formwork, blocking and shoring for this Scope of Work.

    - Supply and install all reinforcing steel, including rebar, welded wire fabric, dowels and accessories, for this Scope of Work's footings and slabs.

    - Haul off dirt spoils and clean and remove debris generated by this Scope of Work; provide containment for concrete truck washout.

    - Provide dust control, street cleaning, barricades and flagging per Nye County Air Quality and Contractor requirements.

- Subcontractor has accounted for, as part of this lump sum Subcontract, the fact that the Contract Documents may not contain all required details, parts, or pieces necessary to provide a complete and functioning system.  Therefore, it is Subcontractor’s responsibility to make reasonably inferable assumptions and allowances, as part of its lump sum proposal, to help account for the design intent and ensure that all elements associated with the Scope of Work comply with all governing codes and regulations.

SCOPE OPTIONS:

- None.

CONSTRUCTION DOCUMENTS:

- Subcontractor shall adhere to all Project specifications within the Project Manual and all Project drawings as referenced in the Attachment C – Enumeration of Documents section of this Subcontract, specifically referencing the following:

- Provide all labor, material, equipment, and services required to furnish and install all items included in the division(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Division 00 – Procurement and Contracting Requirements

- Division 01 - General Requirements

- Provide all labor, material, equipment, and services required to furnish and install all items included in the section(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Section 03 10 00 - Concrete Formwork

- Section 03 20 00 - Concrete Reinforcement

- Section 03 30 00 - Cast-In-Place Concrete

- Section 07 26 00 - Vapor Retarders

- Section 32 13 13 - Concrete Paving

- Section 32 13 73 - Concrete Paving Joint Sealants

- Section 32 16 23 - Sidewalks

- All construction documents referenced in the Attachment C – Enumeration of Documents portion of this Subcontract can be downloaded from the following location:

- Procore – 5 – 26-01-019 - NCSD - Tonopah HS Sports Field Phs'd Replacement

- Invite to be sent to Project team

- Password: Subcontractor generated

Contractor will be using Procore web-based software on this Project to maintain an electronic set of As-Built Documents.  Subcontractor is to furnish electronically all As-Built documents, appropriate warranties and guarantee information, equipment manuals, operations, and maintenance manuals, all of which are a condition to achieving final completion and to receiving final payment.  A Project within Procore has been created for this Project and access will be given to Subcontractor.  All construction documents will be accessible to Subcontractor through Procore.  It will be the responsibility of Subcontractor to create As-Built documents electronically in the field in lieu of providing hard copies.  Contractor will provide training and support on Procore to Subcontractor.

To obtain access, Subcontractor must go to the Procore Software site (www.procore.com) and create a login.  Subcontractor shall create a Username and Password then send a corresponding email address to Contractor’s Project Manager; Contractor’s Project Manager will then email Subcontractor with an invitation to the Project in Procore.  Subcontractor may request additional instructions on how to create a login and Contractor’s Construction Technology department will provide assistance.

- Subcontractor shall adhere to all miscellaneous Project modifications, specifically referencing the following directives:

- Addendum #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #02 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

PROJECT SPECIFIC PROVISIONS:

- Subcontractor shall provide multiple mobilizations as required to complete the Scope of Work as per the dates set forth on the monthly baseline and weekly look-ahead schedules.

- Subcontractor’s foreman, at a minimum, shall attend all daily huddle, weekly work plan, and three phased QAQC plan meetings, which occur a reasonable time before and for the duration of the Subcontract Work on the Project.

- All Submittals shall be submitted in electronic format online using Procore.  Contractor may also request up to six (6) physical hard copies of all submittals.

- Subcontract pricing is based on tariff and/or duties rates in effect as of the date of this Subcontract.  If a net increase in tariffs and/or duties causes a net cost increase on materials, equipment, or products directly required to perform the Subcontract Work, the Subcontractor shall be entitled to a reasonable adjustment to the Subcontract Price to the extent the Prime Contract entitles Contractor to compensation for such increase and then only to the extent of any amount that Contractor may, on behalf of Subcontractor, recover from Owner.  To the extent applicable, any provisions regarding tariff changes in the Prime Contract shall flow down to this Subcontract. Subcontractor must supply reasonable documentation of proof of tariff and/or duties increase and cost impact between the date of this Subcontract and the date of said cost increase, based on an industry approved index associated with that of the affected material. Subcontractor must provide written notice of the cost impact and supporting documentation to Contractor within 7 calendar days of becoming aware. >Do Not Edit this paragraph you can delete all of it or keep all of it KH<

EXCLUSIONS:

- The following items are specifically excluded from the Subcontractor’s Scope of Work:

- Building permits

- Bonds

- NDOT headwall (RCP flared end alternate)

- Concrete pad under existing visitors bleachers

- CMU and CMU reinforcing

- Fence, gate and site sign post footings

- Cost of independent testing and special inspection services

DRAFT REVIEW ONLY - DELETE BEFORE ISSUE

This page is not part of the Subcontract and is not Scope of Work.

RULE 14 REVIEW - obligations removed from the Scope of Work above

Rule 14 keeps out of this exhibit anything the Contract Documents already state, so the Subcontract carries one copy of each obligation rather than two that can drift.

Every line below was drafted, verified and then removed on that basis. All of them still bind the Subcontractor through the document named beneath them. Tick any that should be restated in the Scope of Work above.

A.  Already stated in the Project Manual or on the Drawings

Restating these creates a second, weaker copy of the same obligation.

☐  Provide keyed joints, saw cutting, control joints and expansion joints as indicated and required.

already stated in: Sheet S3-00 typical control and construction joint details; S0-00 general note 6

☐  Provide expansion joint filler and sealants; place and strip white cap at all expansion joints.

already stated in: Section 32 13 73 Concrete Paving Joint Sealants; Sheet A1-20 detail 1 (expansion joint)

☐  Provide control joint layout shop drawings for architectural approval.

already stated in: Division 01 submittal requirements (this is a submittal procedure, not a scope obligation)

☐  Dowel exterior sidewalks to the building slab at entrances and doorways, whether or not detailed.

already stated in: Sheet S3-00 doweled joint detail

☐  Provide 5/8" diameter x 18" long slick dowels at 18" on center minimum at all cold joints, whether shown or not.

already stated in: Sheet S3-00 doweled joint detail (3/4"x16" smooth dowel at 18" o.c.)

☐  Provide concrete sections and finishes for all site concrete as indicated and specified.

already stated in: Section 32 13 13 Concrete Paving; Sheet S3-00 sections

☐  Coordinate threshold requirements per contract documents.

already stated in: Sheet A11-10 door and frame schedule and threshold details generally

☐  Vapor barrier shall be placed directly below the concrete slab-on-grade; tape all joints and penetrations.

already stated in: Section 07 26 00 Vapor Retarders; Sheet S0-00 general note 29

☐  Provide keyed joints, saw cuts, control joints and expansion joints, including compressible filler at CMU walls.

already stated in: Sheet S4-00 control joint detail; Sheet S0-00 masonry notes

☐  Comply with the Geotechnical Report and Contract Documents for excavation, backfill and seismic requirements; most stringent requirement shall prevail.

already stated in: Sheet S0-00 general notes; the Geotechnical Report

☐  The Project has a Class D Seismic Design Category, Seismic Importance Factor 1.0.

already stated in: Sheet S0-00 Design Criteria

☐  Use Type V concrete for all concrete in contact with soil.

already stated in: Sheet S0-00 cast-in-place concrete note 2

☐  Provide all pumping, concrete materials, additives, aggregates, wet curing and curing compounds as specified.

already stated in: Sheet S0-00 general notes 19-20; ACI 305/306

☐  Provide all rebar sizes, grades and lap splices as indicated and required.

already stated in: Sheet S0-00 reinforcing steel notes; Sheet S3-00 rebar lap schedule

☐  Supply, drill and install epoxied smooth dowels if shown.

already stated in: Sheet S3-00 dowel details

☐  Provide Cold and Hot Weather Protection for all concrete placement and finish, per ACI 306.1-90.

already stated in: Sheet S0-00 general note 19

☐  Provide all tests and certifications required for complete and operational systems.

already stated in: Section 01 40 00

☐  Adhere to FF/FL flatness and levelness requirements, including testing, as specified.

already stated in: Section 03 30 00

☐  Include multiple mobilizations as may be required per the Preliminary Construction Schedule and Logistics Plan.

already stated in: this Attachment A, PROJECT SPECIFIC PROVISIONS (carried in the exhibit's mobilization field, not as a scope item)

B.  Stated ONLY in a Scope of Work narrative

These are the ones worth a decision. If the Scope of Work narrative is not an exhibit to the executed Subcontract, striking these removes the obligation outright rather than relocating it.

☐  Maintain batter boards until after slab-on-grade is complete.

already stated in: Scope of Work #030 only

Procedural detail folded into the general layout obligation kept in the exhibit.

☐  Coordinate this scope of work, including layout, with other trade Subcontractors to eliminate conflicts.

already stated in: Scope of Work #030 only

Generic boilerplate; superseded by the named-trade coordination items kept in the exhibit (rule 7).

☐  Coordinate block outs and sleeves in concrete work with other trade subcontractors.

already stated in: Scope of Work #030 only

Superseded by the named version in the exhibit (Wet Utilities, Plumbing, HVAC, Electrical & Low Voltage).

☐  Coordinate with Masonry, Steel, Mechanical, Plumbing, and Electrical & Low Voltage Subcontractors for layout requirements.

already stated in: Scope of Work #030 only

Folded into the named coordination items kept in the exhibit.

☐  Provide a qualified representative onsite for all tests and inspections as required.

already stated in: Scope of Work #030 only

Sahara's proposal excludes 'Testing and inspections fees.' The contested testing-cost boundary is carried instead as an exclusion in the exhibit (cost of the agency, not the cooperation).

☐  Subcontractor responsible for scheduling testing and walking with inspectors to get systems signed off for final approval.

already stated in: Scope of Work #030 only

Same testing-cost conflict as above.

☐  Provide all concrete sealers and cures required at time of placement and finish, compatible with floor finish adhesives.

already stated in: Scope of Work #030 only

Possible overlap with ITB-067 Concrete Finishing (Sealed Concrete alternate). Needs a boundary decision between the two packages before this is restated anywhere.

☐  Clean and maintain trucking access routes for all equipment, including street sweeping as required.

already stated in: Scope of Work #030 only

Folded into the dust control / street cleaning item kept in the exhibit.

☐  Supply Type II, prepare sub-base, and place and compact Type II for the site concrete scope of work.

already stated in: Scope of Work #030 only

Kept in the exhibit, not struck -- listed here only because the spec-citation rationale on 32 13 13 (package record) reads as though RFP-008 carries all Type II under concrete paving. Sahara's own base backup and XL's proposal both price the finish 6" aggregate base under their own site concrete items, which is what the exhibit item now says: this Scope of Work supplies and places its own finish course on subgrade prepared and compacted by others (RFP-008).

C.  Stated in no document at all

Trade means and methods. No document assigns these; they are here only so the list is complete.

☐  Provide all miscellaneous materials required for a complete scope, including tie wire, chairs, dobies and template ties.

already stated in: trade means and methods

☐  Provide chamfers as required.

already stated in: trade means and methods