# ATTACHMENT A

# SCOPE OF WORK

Project Name: NCSD - Tonopah High School Sports Field Replacement

CORE Project No: 26-01-019

Subcontractor:

Henderson Masonry, LLC

400 Mark Leany Drive
Henderson, NV 89011

Phone: 702-567-1536

Contact Person: Mike McComb

Email: mmccomb@hendersonmasonry.com

# LUMP SUM PRICE FOR LABOR, MATERIAL, TAX, AND FREIGHT	     $189,449.00

# No Bond Included

Subcontractor has accounted for, as part of this lump sum Subcontract, any and all potential material, equipment, and labor cost increases over the course of the Project, unless otherwise noted in the Scope of Work.

SCOPE OF WORK:

- Subcontractor shall perform the Scope of Work generally described as:

Masonry

- Subcontractor shall provide a complete turnkey, (i.e., furnish and install), Scope of Work in accordance with Contract Documents to include, but not be limited to:

  - Subcontractor is required to supply Contractor with a material and equipment procurement log as it applies to Subcontractor’s Scope of Work.  Such material and equipment procurement log will show in detail the material product, date ordered, shipping date, and date of delivery to the Project site. Subcontractor shall provide documentation from each manufacturer and/or distributor confirming the dates shown on the procurement log.  Subcontractor agrees to update such procurement log and shall transmit either in hard copy or electronic format to the Contractor, on a bi-weekly basis, or more frequently as reasonably required by Contractor.

  - Subcontractor shall provide to Contractor cost flow projections monthly including computations and projections related to this Scope of Work. Projections shall include costs from and related to, manpower, coordination, supervision, equipment, and material for completing this Scope of Work.

  - Building Masonry - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Supply and install all masonry and masonry accessories at the concessions building as indicated.

    - Includes stem walls, walls, pilasters, columns, bond beams, masonry lintels, and control joints.

    - Includes integral water repellent in all block, mortar and grout exposed above grade.

    - Supply and install all CMU reinforcing required for this Scope of Work.

    - Coordinate masonry reinforcing laps and dowel layout with Concrete Subcontractor.

    - Receive, unload and inventory all steel embeds supplied by others.

    - Includes layout, installation and grouting of all embeds, bearing plates, anchor bolts and sleeves supplied by others.

    - Includes drypack under bearing plates and solid grouting of beam pockets after structural steel erection.

    - Layout, install, brace and grout all hollow metal door frames supplied by others.

    - Coordinate frame delivery with Doors, Frames & Hardware Subcontractor for setting during masonry construction.

    - Coordinate penetrations, sleeves and chases in masonry with Plumbing, HVAC and Electrical & Low Voltage Subcontractors.

    - Coordinate surface applied features and smooth face wall returns at entrances, including cameras, speakers, wall pack lights and hose bibs.

    - Clean and remove debris from top of footings as required to place masonry units.

- Subcontractor has accounted for, as part of this lump sum Subcontract, the fact that the Contract Documents may not contain all required details, parts, or pieces necessary to provide a complete and functioning system.  Therefore, it is Subcontractor’s responsibility to make reasonably inferable assumptions and allowances, as part of its lump sum proposal, to help account for the design intent and ensure that all elements associated with the Scope of Work comply with all governing codes and regulations.

SCOPE OPTIONS:

- None.

CONSTRUCTION DOCUMENTS:

- Subcontractor shall adhere to all Project specifications within the Project Manual and all Project drawings as referenced in the Attachment C – Enumeration of Documents section of this Subcontract, specifically referencing the following:

- Provide all labor, material, equipment, and services required to furnish and install all items included in the division(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Division 00 – Procurement and Contracting Requirements

- Division 01 - General Requirements

- Provide all labor, material, equipment, and services required to furnish and install all items included in the section(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Section 04 05 03 - Masonry Mortaring and Grouting

- Section 04 20 16 - Reinforced Unit Masonry

- All construction documents referenced in the Attachment C – Enumeration of Documents portion of this Subcontract can be downloaded from the following location:

- Procore – 5 – 26-01-019 - NCSD - Tonopah HS Sports Field Phs'd Replacement

- Invite to be sent to Project team

- Password: Subcontractor generated

Contractor will be using Procore web-based software on this Project to maintain an electronic set of As-Built Documents.  Subcontractor is to furnish electronically all As-Built documents, appropriate warranties and guarantee information, equipment manuals, operations, and maintenance manuals, all of which are a condition to achieving final completion and to receiving final payment.  A Project within Procore has been created for this Project and access will be given to Subcontractor.  All construction documents will be accessible to Subcontractor through Procore.  It will be the responsibility of Subcontractor to create As-Built documents electronically in the field in lieu of providing hard copies.  Contractor will provide training and support on Procore to Subcontractor.

To obtain access, Subcontractor must go to the Procore Software site (www.procore.com) and create a login.  Subcontractor shall create a Username and Password then send a corresponding email address to Contractor’s Project Manager; Contractor’s Project Manager will then email Subcontractor with an invitation to the Project in Procore.  Subcontractor may request additional instructions on how to create a login and Contractor’s Construction Technology department will provide assistance.

- Subcontractor shall adhere to all miscellaneous Project modifications, specifically referencing the following directives:

- Addendum #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #02 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

PROJECT SPECIFIC PROVISIONS:

- Subcontractor shall provide multiple mobilizations as required to complete the Scope of Work as per the dates set forth on the monthly baseline and weekly look-ahead schedules.

- Subcontractor’s foreman, at a minimum, shall attend all daily huddle, weekly work plan, and three phased QAQC plan meetings, which occur a reasonable time before and for the duration of the Subcontract Work on the Project.

- All Submittals shall be submitted in electronic format online using Procore.  Contractor may also request up to six (6) physical hard copies of all submittals.

- Subcontract pricing is based on tariff and/or duties rates in effect as of the date of this Subcontract.  If a net increase in tariffs and/or duties causes a net cost increase on materials, equipment, or products directly required to perform the Subcontract Work, the Subcontractor shall be entitled to a reasonable adjustment to the Subcontract Price to the extent the Prime Contract entitles Contractor to compensation for such increase and then only to the extent of any amount that Contractor may, on behalf of Subcontractor, recover from Owner.  To the extent applicable, any provisions regarding tariff changes in the Prime Contract shall flow down to this Subcontract. Subcontractor must supply reasonable documentation of proof of tariff and/or duties increase and cost impact between the date of this Subcontract and the date of said cost increase, based on an industry approved index associated with that of the affected material. Subcontractor must provide written notice of the cost impact and supporting documentation to Contractor within 7 calendar days of becoming aware. >Do Not Edit this paragraph you can delete all of it or keep all of it KH<

EXCLUSIONS:

- The following items are specifically excluded from the Subcontractor’s Scope of Work:

- Building permits

- Bonds

- Concrete footings and foundation dowels

- Caulking, sealants and backer rod at masonry

- Surface applied waterproofing, sealers and anti-graffiti coatings

- Cost of independent testing and special inspection services

- Top of wall nailers and pressure treated plywood

DRAFT REVIEW ONLY - DELETE BEFORE ISSUE

This page is not part of the Subcontract and is not Scope of Work.

RULE 14 REVIEW - obligations removed from the Scope of Work above

Rule 14 keeps out of this exhibit anything the Contract Documents already state, so the Subcontract carries one copy of each obligation rather than two that can drift.

Every line below was drafted, verified and then removed on that basis. All of them still bind the Subcontractor through the document named beneath them. Tick any that should be restated in the Scope of Work above.

A.  Already stated in the Project Manual or on the Drawings

Restating these creates a second, weaker copy of the same obligation.

☐  Provide CMU conforming to ASTM C90, Grade N, medium weight, Type II/V cement, Type I moisture controlled.

already stated in: Section 04 20 16 para 2.02.A; S0-00 CMU note 3

☐  Individual units shall attain 2,800 psi compressive strength and the masonry assembly shall attain an f'm of 2,000 psi.

already stated in: S0-00 CMU note 2; Section 04 20 16 para 2.02.A

Conflict: the spec says 2000 psi minimum for units, S0-00 says 2800 psi. Stricter reading governs.

☐  Provide fully grouted CMU walls and stem walls.

already stated in: S0-00 CMU note 8, grout cells solid in all walls; S3-01 details 1 through 4

☐  Supply and place all mortar and grout, including test samples, pigment and admixture as specified.

already stated in: Section 04 05 03 paras 2.03 through 2.06

☐  Place masonry control joints at 30'-0" maximum spacing, and not within 4'-0" of any wall opening.

already stated in: S4-00 detail 5 note 1; Section 04 20 16 paras 3.10.F and 3.10.G

Conflict: the spec allows 40 ft, S4-00 requires 30'-0". Of the items on this page this is the one I would put back.

☐  Tool all exposed mortar joints to match the existing masonry at the site.

already stated in: Section 04 20 16 para 3.03.E

☐  Includes 50 of each size, color and type of unit, delivered to the Owner as extra materials.

already stated in: Section 04 20 16 para 1.12.B

No bidder mentioned attic stock, so nobody has priced delivering it.

☐  Furnish and install all non-shrink grout at all embeds set into masonry construction.

already stated in: S0-00 steel note 13, non-shrink non-metallic 10,000 psi

The grouting obligation itself survives in the scope above; only the product description was struck.

☐  Verify all mounting heights against the Architectural and MEP drawings.

already stated in: Section 04 20 16 para 3.01; the drawings themselves

☐  Furnish and install all wall bracing between CMU wall construction and structural steel erection.

already stated in: Section 04 20 16 para 3.02.B

☐  Provide temporary shoring and bracing at all masonry construction and wall openings to resist lateral deflection.

already stated in: Section 04 20 16 para 3.02.B; S0-00 masonry note 4

☐  Remove all shoring and bracing after wall mortar has reached design strength.

already stated in: Section 04 20 16 para 3.02.B; S0-00 masonry note 4

☐  Provide cold and hot weather protection for all masonry work as specified.

already stated in: Section 04 20 16 para 1.10; Section 04 05 03 para 1.07

☐  Provide approved, dated and detailed reinforcing steel shop drawings showing sequencing and all areas of work prior to start.

already stated in: Section 04 20 16 para 1.04.B; Section 01 33 00

☐  Provide design mixes, product data and manufacturer's certificates for all masonry units, mortar, grout and reinforcement.

already stated in: Section 04 05 03 para 1.04; Section 04 20 16 para 1.04

☐  Submit 4 samples of block units illustrating color, texture and the extremes of color range.

already stated in: Section 04 20 16 para 1.04.D

☐  Construct an 8' x 8' masonry mock-up including mortar, accessories and door framing elements, where directed.

already stated in: Section 04 20 16 para 1.08

☐  Remove the mock-up at completion of masonry work.

already stated in: Section 04 20 16 para 1.08.D

☐  Provide all tests and certifications required for complete and operational systems.

already stated in: Section 01 40 00

☐  Clean, point up and repair all masonry work as required for application of final finishes by others.

already stated in: Section 04 20 16 para 3.14

☐  Clean and remove from site all debris and unsatisfactory materials generated from this Scope of Work.

already stated in: Section 01 74 00

☐  Comply with the requirements of the Geotechnical Report and the Contract Documents; the most stringent requirement shall prevail.

already stated in: the Geotechnical Report and the Contract Documents generally

☐  Provide a competent foreman who shall participate in the daily huddle and weekly workplan meetings.

already stated in: this Attachment A, PROJECT SPECIFIC PROVISIONS

☐  Include multiple mobilizations as may be required per the Preliminary Construction Schedule and Logistics Plan.

already stated in: this Attachment A, PROJECT SPECIFIC PROVISIONS

B.  Stated ONLY in a Scope of Work narrative

These are the ones worth a decision. If the Scope of Work narrative is not an exhibit to the executed Subcontract, striking these removes the obligation outright rather than relocating it.

☐  Provide layout for formwork and rough bucks at all wall openings in masonry construction.

already stated in: Scope of Work #031 only

Henderson's proposal marks Window/Door Bucks EXCLUDED. Contested.

☐  If schedule allows, provide preconstruction prism testing as a separate grout pour.

already stated in: Scope of Work #031 only

Henderson's proposal marks Testing EXCLUDED. Contested.

☐  Provide a qualified representative onsite for all tests, special inspections and inspections as required.

already stated in: Scope of Work #031 only

Henderson's proposal marks Testing EXCLUDED. Contested.

☐  Schedule all testing and walk with inspectors to obtain sign-off of all systems for final approval.

already stated in: Scope of Work #031 only

Henderson's proposal marks Testing EXCLUDED. Contested.

☐  Provide dust control, street cleaning, barricades and flagging per Nye County Air Quality and Contractor requirements.

already stated in: Scope of Work #031 only

Henderson's proposal marks Barricades EXCLUDED. Contested.

☐  Supply and maintain rebar safety caps for this Scope of Work.

already stated in: Scope of Work #031 and #030 only

A handoff: #030 maintains caps until this Subcontractor assumes responsibility. Neither party's exhibit says when.

☐  Coordinate delivery and layout of all masonry wall embeds with the Structural Steel Subcontractor.

already stated in: Scope of Work #033 only, which is another package's narrative

RFP-033 double-claims the CMU bearing plates. This line is what would settle it from this side.

☐  Submit masonry control joint layout and elevation shop drawings for approval.

already stated in: Scope of Work #031; Section 04 20 16 para 3.10.E requires Engineer approval but not the submittal

This submittal is where the 30 ft / 40 ft spacing conflict surfaces.

☐  Provide containment for mortar and grout wash-out at the location provided on site.

already stated in: Scope of Work #031 only

☐  Utilize a wet saw for all CMU cutting and grinding to minimize dust.

already stated in: Scope of Work #031 only; Nye County Air Quality requirements

☐  Coordinate mock-up size and requirements with Contractor's onsite Superintendent.

already stated in: Scope of Work #031 only

☐  Cooperate in the layout of masonry work from building corners and finish floor elevations, including embeds, control joints, footing rebar and all openings.

already stated in: Scope of Work #031 only

☐  Provide layout from gridlines and benchmarks provided and approved by Contractor.

already stated in: Scope of Work #031 only

☐  Provide all hoisting for masonry materials and rebar systems.

already stated in: Scope of Work #031 only

C.  Stated in no document at all

Trade means and methods. No document assigns this one; it is here only so the list is complete.

☐  Provide all scaffolding required for this Scope of Work.

basis: John Jackson, Kemper and XL each priced it as their own