# ATTACHMENT A

# SCOPE OF WORK

Project Name: NCSD - Tonopah High School Sports Field Replacement

CORE Project No: 26-01-019

Subcontractor:

Quantum Electric, LLC

3151 Manzanita Lane
Elko, NV 89801

Phone: 775-777-2000

Contact Person: Joe Curry

Email: curry.qe@frontier.com

# LUMP SUM PRICE FOR LABOR, MATERIAL, TAX, AND FREIGHT	     $1,074,541.00

# No Bond Included

Subcontractor has accounted for, as part of this lump sum Subcontract, any and all potential material, equipment, and labor cost increases over the course of the Project, unless otherwise noted in the Scope of Work.

SCOPE OF WORK:

- Subcontractor shall perform the Scope of Work generally described as:

Electrical & Low Voltage Systems

- Subcontractor shall provide a complete turnkey, (i.e., furnish and install), Scope of Work in accordance with Contract Documents to include, but not be limited to:

  - Subcontractor is required to supply Contractor with a material and equipment procurement log as it applies to Subcontractor’s Scope of Work.  Such material and equipment procurement log will show in detail the material product, date ordered, shipping date, and date of delivery to the Project site. Subcontractor shall provide documentation from each manufacturer and/or distributor confirming the dates shown on the procurement log.  Subcontractor agrees to update such procurement log and shall transmit either in hard copy or electronic format to the Contractor, on a bi-weekly basis, or more frequently as reasonably required by Contractor.

  - Subcontractor shall provide to Contractor cost flow projections monthly including computations and projections related to this Scope of Work. Projections shall include costs from and related to, manpower, coordination, supervision, equipment, and material for completing this Scope of Work.

  - Site Electrical & Low Voltage Systems - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Safe-off and disconnect existing electrical and low voltage equipment scheduled for demolition, including the concessions building, press box panel, field lighting and scoreboard.

    - Salvage the sports field loudspeakers, PA system cabinet, wireless transmitter and microphones prior to demolition; coordinate removal and storage with Contractor.

    - Supply and install the new site transformer, Musco lighting controller and weatherproof enclosures as indicated.

    - Coordinate transformer mounting requirements with Scoreboard Subcontractor.

    - Includes power and data connections to the field lighting, scoreboard, press box and irrigation controller.

    - Includes Low Voltage pathway from the existing field in-ground boxes back to the High School IT Room, including conduit, fiber and CAT6A cabling.

    - Includes exterior wall-mounted weatherproof pull boxes and patch cables for the Low Voltage pathway, as specified.

    - Includes sawcutting, patch-back and repair as required at the existing High School building, to match existing finishes.

    - Coordinate work at the existing High School building with Contractor and Owner.

    - Coordinate layout of sleeves, block-outs and embedded items with Masonry and Concrete Subcontractors.

  - Elementary School Electrical Demolition - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Safe-off and disconnect electrical and low voltage systems, including fire alarm systems and feeders, at the Elementary School buildings scheduled for demolition.

    - Coordinate demolition sequencing with the Abatement & Building Wrecking Subcontractor.

  - Trenching, Excavation & Foundations - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Includes hard-dig excavation, including Caliche, for all trenching and foundations under this Scope of Work.

    - Includes trenching for Landscape Irrigation control power.

    - Includes excavation, reinforcing, concrete, anchor bolts and drypack for the 4 Musco sports field light pole foundations, per Musco's precast base.

    - Assumes spoils generated by this Scope of Work may be stockpiled on site; offsite haul-off is excluded.

    - Coordinate underground piping location and depth with the Concrete Subcontractor to minimize sleeving.

    - Coordinate site utility layout with the Earthwork and Landscape & Irrigation Subcontractors.

  - Sports Field Lighting - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Supply and install the Musco sports field lighting system, including poles, luminaires, conduit and wiring, per the Lighting Fixture Schedule.

    - Includes footing design for the sports field light poles, coordinated with Musco's precast base and reinforcing.

    - Includes a photometric light study showing footcandle coverage across the field and track.

    - Includes programming and commissioning of the Musco lighting control system.

  - Building Electrical - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Includes all panels, receptacles, switches, and interior and exterior lighting and lighting controls as scheduled.

    - Includes exterior emergency light fixtures as required by code, whether or not shown on the drawings.

    - Provide a light fixture in every room, whether or not shown on the drawings.

    - Includes temporary power to the jobsite, 200A at the trailer yard and 200A at the new building.

    - Includes power and control wiring to the electric operator at the coiling counter shutter, Door 106A, per Door Hardware Set #4/#5.

    - Coordinate ceiling-mounted fixture layout with HVAC and Acoustical Ceiling Subcontractors, centered in the acoustical tile.

    - Includes final electrical connections to food service equipment and Owner-furnished, Owner-installed equipment.

    - Includes final connections to Mechanical and Plumbing equipment and to smoke detectors.

    - Includes a 120V power circuit for controls at each equipment controller, whether or not shown on the drawings.

    - Supply only, F.O.B. jobsite, access doors and panels for concealed electrical work, keyed alike; installation by Framing Subcontractor.

  - Low Voltage, Communications, Audio-Visual & Security Systems - Provide all materials, labor, equipment, and supervision for a complete Scope of Work per plans and specifications. This Scope of Work shall include, but not be limited to:

    - Includes low voltage systems in the Concessions Building, Press Box and Ticket Booth.

    - Install Owner Furnished, Contractor Installed (OFCI) low voltage equipment, including salvaged equipment, as indicated.

    - Includes final low voltage connections to equipment furnished by others.

    - Includes conduit pathway and mule tape stubbed for future fire alarm, per plans.

    - Supply and install the CCTV video management system and video storage, and install Owner-provided cameras and mounts.

    - Includes reinstallation and final connections for the salvaged sports field sound and paging equipment in the new Press Box.

    - Coordinate Audio-Visual final connections with the Press Box manufacturer.

  - General Scope Requirements

    - Provide a qualified representative on-site for all tests and inspections, and coordinate scheduling with inspectors for final approval.

    - Complete final utility adjustments prior to site concrete placement.

    - Seal all through-wall and through-floor penetrations with acoustical sealant.

    - Coordinate roof penetrations with Roofing Subcontractor; space penetrations a minimum of 12 inches apart.

    - Coordinate electrical testing and commissioning requirements with Owner's consultant.

    - Coordinate with HVAC & Building Controls Subcontractor for interface with the Building Control Systems.

    - Where raceways are architecturally exposed, install in a neat, aesthetic manner and mock up as directed by the Superintendent.

- Subcontractor has accounted for, as part of this lump sum Subcontract, the fact that the Contract Documents may not contain all required details, parts, or pieces necessary to provide a complete and functioning system.  Therefore, it is Subcontractor’s responsibility to make reasonably inferable assumptions and allowances, as part of its lump sum proposal, to help account for the design intent and ensure that all elements associated with the Scope of Work comply with all governing codes and regulations.

SCOPE OPTIONS:

- None.

CONSTRUCTION DOCUMENTS:

- Subcontractor shall adhere to all Project specifications within the Project Manual and all Project drawings as referenced in the Attachment C – Enumeration of Documents section of this Subcontract, specifically referencing the following:

- Provide all labor, material, equipment, and services required to furnish and install all items included in the division(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Division 00 – Procurement and Contracting Requirements

- Division 01 - General Requirements

- Provide all labor, material, equipment, and services required to furnish and install all items included in the section(s) of the Project Manual listed below, as related to Subcontractor’s Scope of Work:

- Section 26 00 10 - General Electrical Requirements

- Section 26 05 00 - Common Work Results for Electrical

- Section 26 05 05 - Selective Demolition for Electrical

- Section 26 05 19 - Low-Voltage Electrical Power Conductors and Cables

- Section 26 05 26 - Grounding and Bonding for Electrical Systems

- Section 26 05 29 - Hangers and Supports for Electrical Systems

- Section 26 05 33.13 - Conduit for Electrical Systems

- Section 26 05 33.16 - Boxes for Electrical Systems

- Section 26 05 53 - Identification for Electrical Systems

- Section 26 05 83 - Wiring Connections

- Section 26 08 00 - Electrical Testing and Commissioning Requirements

- Section 26 09 23 - Lighting Control Devices

- Section 26 22 00 - Low-Voltage Transformers

- Section 26 24 16 - Panelboards

- Section 26 27 26 - Wiring Devices

- Section 26 28 13 - Fuses

- Section 26 28 16.16 - Enclosed Switches

- Section 26 29 13 - Enclosed Controllers

- Section 26 43 00 - Surge Protective Devices

- Section 26 51 00 - Interior Lighting

- Section 26 56 00 - Exterior Lighting

- Section 27 00 00 - Communications - General

- Section 08 31 00 - Access Doors and Panels

- All construction documents referenced in the Attachment C – Enumeration of Documents portion of this Subcontract can be downloaded from the following location:

- Procore – 5 – 26-01-019 - NCSD - Tonopah HS Sports Field Phs'd Replacement

- Invite to be sent to Project team

- Password: Subcontractor generated

Contractor will be using Procore web-based software on this Project to maintain an electronic set of As-Built Documents.  Subcontractor is to furnish electronically all As-Built documents, appropriate warranties and guarantee information, equipment manuals, operations, and maintenance manuals, all of which are a condition to achieving final completion and to receiving final payment.  A Project within Procore has been created for this Project and access will be given to Subcontractor.  All construction documents will be accessible to Subcontractor through Procore.  It will be the responsibility of Subcontractor to create As-Built documents electronically in the field in lieu of providing hard copies.  Contractor will provide training and support on Procore to Subcontractor.

To obtain access, Subcontractor must go to the Procore Software site (www.procore.com) and create a login.  Subcontractor shall create a Username and Password then send a corresponding email address to Contractor’s Project Manager; Contractor’s Project Manager will then email Subcontractor with an invitation to the Project in Procore.  Subcontractor may request additional instructions on how to create a login and Contractor’s Construction Technology department will provide assistance.

- Subcontractor shall adhere to all miscellaneous Project modifications, specifically referencing the following directives:

- Addendum #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #01 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

- Clarification #02 - Provide all material, equipment, and services as required to furnish and install all items included in directive, as they relate to the Scope of Work.

PROJECT SPECIFIC PROVISIONS:

- Subcontractor shall provide multiple mobilizations as required to complete the Scope of Work as per the dates set forth on the monthly baseline and weekly look-ahead schedules.

- Subcontractor’s foreman, at a minimum, shall attend all daily huddle, weekly work plan, and three phased QAQC plan meetings, which occur a reasonable time before and for the duration of the Subcontract Work on the Project.

- All Submittals shall be submitted in electronic format online using Procore.  Contractor may also request up to six (6) physical hard copies of all submittals.

- Subcontract pricing is based on tariff and/or duties rates in effect as of the date of this Subcontract.  If a net increase in tariffs and/or duties causes a net cost increase on materials, equipment, or products directly required to perform the Subcontract Work, the Subcontractor shall be entitled to a reasonable adjustment to the Subcontract Price to the extent the Prime Contract entitles Contractor to compensation for such increase and then only to the extent of any amount that Contractor may, on behalf of Subcontractor, recover from Owner.  To the extent applicable, any provisions regarding tariff changes in the Prime Contract shall flow down to this Subcontract. Subcontractor must supply reasonable documentation of proof of tariff and/or duties increase and cost impact between the date of this Subcontract and the date of said cost increase, based on an industry approved index associated with that of the affected material. Subcontractor must provide written notice of the cost impact and supporting documentation to Contractor within 7 calendar days of becoming aware. >Do Not Edit this paragraph you can delete all of it or keep all of it KH<

EXCLUSIONS:

- The following items are specifically excluded from the Subcontractor’s Scope of Work:

- Building permits

- Bonds

- RGBW color-changing and show-lighting fixtures at the sports field light poles

- Fire detection and alarm system

- Wired communication connection to the scoreboard

- Active network equipment, including network switches and uninterruptible power supplies

- Configuration of the security camera and paging system to interface with existing systems

- Offsite haul-off of spoils generated by this Scope of Work

DRAFT REVIEW ONLY - DELETE BEFORE ISSUE

This page is not part of the Subcontract and is not Scope of Work.

RULE 14 REVIEW - obligations removed from the Scope of Work above

Rule 14 keeps out of this exhibit anything the Contract Documents already state, so the Subcontract carries one copy of each obligation rather than two that can drift.

Every line below was drafted, verified and then removed on that basis. All of them still bind the Subcontractor through the document named beneath them. Tick any that should be restated in the Scope of Work above.

A.  Already stated in the Project Manual or on the Drawings

Restating these creates a second, weaker copy of the same obligation.

☐  Provide all cabling, testing, and terminations as required for a complete scope of work.

already stated in: Section 26 00 10 para 1.2.A (complete functioning systems clause); Section 26 08 00

☐  Supply and install all sleeves and flashings for this scope of work and any coring, if not sleeved; provide coordination drawings showing locations and sizes for all sleeved penetrations.

already stated in: Section 26 00 10 para 3.6 Penetrations

☐  Supply and install all required site electrical and low voltage identification.

already stated in: Section 26 05 53 Identification for Electrical Systems

☐  Request Call Before You Dig, provide excavation support and hazard protection, shore and brace trenches, dewater, and control dust per Nye County Air Quality requirements.

already stated in: Section 26 00 10 paras 3.7.G-3.7.I; Nye County Air Quality requirements

☐  MC Cable is permitted only as specified and shall not be bundled due to overheating risk; maintain separation from adjacent cables per the UL Listing.

already stated in: Section 26 05 19 para 2.1.F

☐  Supply and install all electrical switchgear as indicated and required.

already stated in: Section 26 00 10 para 1.2.A (complete functioning systems clause)

☐  Supply and install mechanically attached electrical placards for Electrical Disconnects and Main Electrical Rooms.

already stated in: Section 26 05 53

☐  Supply and install emergency light fixtures, including 90-minute battery backup.

already stated in: Section 26 51 00 para 2.3.B (90-minute minimum output required)

☐  Includes all lighting mounting clips and hardware required for a complete installation.

already stated in: Section 26 00 10 para 1.2.A (complete functioning systems clause)

☐  Telephone backboards in the ER's and TR's as indicated and required.

already stated in: Section 27 00 00 para 2.6 Plywood Backboard

☐  Provide / install all equipment racks and active equipment as indicated.

already stated in: Section 27 00 00 para 1.1.A.1 (Contractor furnishes and installs network switches and UPS)

This section directly conflicts with the Basis of GMP's project-wide exclusion of Active Network Equipment. See _open_pm_items.

☐  Provide grounding at all TR equipment and racks.

already stated in: Section 26 05 26; Section 27 00 00

☐  Supply and install all required low voltage identification.

already stated in: Section 27 00 00 para 3.3 Labeling; Section 26 05 53

☐  Supply and install engineered seismic design, bracing, restraints and supports for all equipment; comply with the Geotechnical Report and Contract Documents; the most stringent requirement shall prevail.

already stated in: Section 26 05 29; the Geotechnical Report

☐  All supports and hangers shall be coordinated with architectural and structural requirements and attached to structural steel framing members; piping and hangers shall not hang from decking.

already stated in: Section 26 05 29 para 3.2.D

☐  Start-up all systems, including any required training, commissioning, testing and balancing programs, and final adjustments.

already stated in: Section 26 08 00

☐  Provide all disconnects, raceways, boxes, conductors and final connections to plumbing and HVAC equipment per Divisions 22 and 23.

already stated in: E0-01 general note 11; Divisions 22 and 23

☐  Comply with warranty requirements as specified, including coordination with any specified insurance requirements.

already stated in: Section 26 00 10 para 1.15

☐  Unless otherwise stated, all overhead systems must be labeled per ASME 13.1 for all State of Nevada projects.

already stated in: E0-01 general notes 31-37 (color coding and identification)

☐  Provide submittals and shop drawings as specified and required for all Electrical and Low Voltage systems.

already stated in: Section 26 00 10 para 1.7; Section 27 00 00 para 1.4

☐  Provide all tests and certifications required for complete and operational systems.

already stated in: Section 26 08 00

☐  Coordinate with Architectural and Structural drawings for required clearances.

already stated in: Section 26 00 10 para 1.5.C

B.  Stated ONLY in a Scope of Work narrative

These are the ones worth a decision. If the Scope of Work narrative is not an exhibit to the executed Subcontract, striking these removes the obligation outright rather than relocating it.

☐  Provide complete and operational fire detection and alarm system with voice evacuation, smoke detectors in restrooms, and obtain permit from the AHJ.

already stated in: Scope of Work #103 only

Superseded by the 08.04.26 ruling that fire alarm systems are an express GMP Exclusion. Carried in the exhibit as an exclusion by name instead, since the narrative still describes a full system.

☐  Provide temporary electrical service and distribution system, and temporary lighting for construction operations, until permanent lighting is operational.

already stated in: Scope of Work #103 only

☐  Excavate and pour light pole bases.

already stated in: Scope of Work #103 only

Duplicate within the narrative itself of the foundation obligation already carried in the Trenching, Excavation & Foundations group.

☐  Supply and install all anchor bolts, nuts and templates for light poles.

already stated in: Scope of Work #103 only

Folded into the light pole foundation item already carried.

☐  Coordinate layout and installation of lighting and ceiling-mounted fixtures with HVAC Subcontractor and Acoustical Ceiling Subcontractor; center fixtures in the acoustical tile.

already stated in: Scope of Work #103 only

A condensed version of this coordination item is carried in the exhibit's Building Electrical group.

C.  Stated in no document at all

Trade means and methods. No document assigns this one; it is here only so the list is complete.

☐  All materials stored inside the building shall be on wheels.

already stated in: Scope of Work #103 only, appears in no other document and no bidder addressed it

☐  Crane to be provided from Elko.

already stated in: Quantum's own 05.20.26 scope-review agenda -- the bidder's logistics assumption, not a contract requirement