## release priority
Rank | Tier | Package | Phase Code | Title | Carried Subcontractor | Carried Value | Binding Long-Lead Chain | First Field Activity Needing This Sub | Field Need Date | Sub mit | Rev iew | Proc ure | Exec | Total | Basis | Attachment A Draft By | Latest Release Date | Work Days of Slack | Why This Rank
1 | 1 — RELEASE NOW | RFP-033 | 05-1000-10000 | Structural Steel & Ornamental Metals | Corona Steel | 166281 | Joist & deck — deferred submittal | Steel, Joists, & Deck Erection | 2027-05-03 | 40 | 15 | 100 | 15 | 170 | sched | 2026-08-24 | 2026-09-07 | 21 | IDs 25/48/73 for anchor bolts, 24/60/87 for steel, 42/90/81 for joist and deck. JOIST & DECK BINDS: 40 d submit + 15 d review + 100 d procure = 170 working days back from erection on 5/3/27, the longest single chain on the job, and it is a deferred submittal so the review runs through the building official rather than stopping at the EOR. The steel itself is close behind at 165 days, carrying the longest submittal review on the job at 30 days (ID 60). And a third obligation lands far earlier than either: the ANCHOR BOLTS are needed 2/15/27 for foundations, two and a half months before erection, embedded in RFP-030's concrete. • Longest submittal review on the job (30 d) with no slack behind it • Delegated design: joist & deck is a deferred submittal • OPEN: goal post structural design is listed as a deferred submittal on G0-00 and is assigned to no package
2 | 1 — RELEASE NOW | RFP-103 | 26-1000-10000 | Electrical & Low Voltage Systems (incl. Sports Field Lighting) | Quantum Electric | 1074541 | Electrical lighting package | Set Electrical Equipment | 2027-07-06 | 40 | 15 | 140 | 15 | 210 | sched | 2026-09-01 | 2026-09-15 | 27 | Three separate chains, IDs 29/52/70, 31/47/67 and 30/63/84, and the one that binds is the least obvious. Rough-in material for the 2/8/27 underground needs release by 11/13/26; the Musco poles by 11/2/26; but the electrical LIGHTING PACKAGE runs 40 d submit + 15 d review + 140 d procure, and 210 working days back from Set Electrical Equipment on 7/6/27 lands on 9/15/26. That 140-day procurement is the longest on the job and is what defines the 5/3/27 Material Procurement Complete milestone -- the schedule's own last procurement date belongs to this package. • Largest subcontract on the job at $1,074,541 • Longest procurement on the job (140 d) and it defines Material Procurement Complete • Delegated design: Musco pole foundations and sports lighting photometrics • Single-source manufacturer (Musco) — no recovery by rebidding • OPEN: the ASI formalizing the no-fire-alarm direction has not issued; the GMP Exclusion covers the money but not the drawings
3 | 1 — RELEASE NOW | RFP-002 | 02-1110-10000 | Abatement & Building Wrecking | Northstar Contracting Group | 741912 | NESHAP/NDEP notification and abatement work plan | Abatement ahead of Demo | 2026-11-24 | 15 | 10 | 0 | 15 | 40 | judgment | 2026-09-15 | 2026-09-29 | 37 | A regulatory clock, not a material clock. NESHAP requires written notification before an abatement start, and NDEP/NV OSHA want the work plan and licenses first. The schedule carries no submittal line for abatement at all, and abatement has to finish before the 12/3/26 wrecking. • Regulatory lead, not material lead — notification periods cannot be compressed • Asbestos: an abatement failure stops the demolition that stops everything else • OPEN: the ES campus demolition alternate is worded identically in RFP-002 and RFP-008 and it is still unresolved whether it splits by trade
4 | 2 — next 60 work days | ITB-008 | 02-1010-10000 | Surveying, Layout & Staking | Prewitt Land Surveying | 80767.5 | Survey control and staking | Temp Fence & Mobilize | 2026-11-24 | 10 | 5 | 0 | 15 | 30 | judgment | 2026-09-29 | 2026-10-13 | 47 | No submittal or procurement activity anywhere in the schedule. Control has to be set before the first field activity, so mobilization is the need date, not a later staking task.
5 | 2 — next 60 work days | ITB-089 | 11-0101-10000 | Scoreboards | YESCO | 99483 | Deferred structural submittal and fabrication | Install Musco Light Poles | 2027-03-08 | 30 | 15 | 40 | 15 | 100 | judgment | 2026-10-05 | 2026-10-19 | 51 | SCHEDULE GAP -- the scoreboard has no procurement activity. Sheet G0-00 lists it as a deferred submittal, so it carries delegated design through the AHJ. Its foundation is RFP-030's pour and its feed is RFP-103's conduit, so both of those need its layout. • Deferred submittal with delegated design and no procurement activity
6 | 2 — next 60 work days | RFP-008 | 31-2000-10000 | Site Demolition, Salvage, Earthwork, Asphalt Paving, Wet Utilities, & Site Signage & Striping | TAB Contractors (New-Com) | 1741321 | Mobilization — first sub on the field | Temp Fence & Mobilize | 2026-11-24 | 10 | 0 | 0 | 15 | 25 | judgment | 2026-10-06 | 2026-10-20 | 52 | Schedule IDs 34/54/71 give the utility chain 15/15/15 with procurement complete 9/29/26, which has float. Mobilization is what binds: this sub opens the site and every other site package sequences behind it. • First sub on the field; every site package sequences behind it • OPEN: package title carries site signage and striping the narrative never scopes and the sub excluded twice • OPEN: accepted VE #10 at −$16,750 has no matching line in the sub's own homework • OPEN: stockpiling — narrative prohibits, GMP assumes, VE #10 relies on it
7 | 2 — next 60 work days | RFP-045 | 07-4100-10000 | Metal Roofing, Fascia & Soffit Panels | Foursquare Roof and Walls | 142585 | Metal panels | Roof, Fascia, Soffit Panels | 2027-06-08 | 30 | 15 | 100 | 15 | 160 | sched | 2026-10-13 | 2026-10-27 | 57 | IDs 37/57/76 and 35/58/78. Two 100-day procurements against the same field date. Berridge C-Lock per the 08.06.26 B1 ruling -- that ruling reverses a written architect's RFI answer and has to be settled before release or the sub orders the wrong panel and the 100 days start over. • OPEN: the 08.06.26 B1 ruling puts the GMP over RFI #23, reversing a written architect's answer — settle before release or the sub buys the wrong panel
8 | 3 — next 90 work days | RFP-030 | 03-1000-10000 | Concrete | Sahara Concrete | 1278459.84 | Footing rebar | Retaining Walls / Build Building Pad | 2027-02-08 | 15 | 15 | 15 | 15 | 60 | sched | 2026-11-02 | 2026-11-16 | 71 | Schedule IDs 22/49/68 for rebar. The real constraint is not rebar, it is everything embedded in this sub's concrete: RFP-033 anchor bolts, ITB-019 equipment sleeves, RFP-094 bleacher anchors, ITB-078 flagpole foundations, and the trench drains ruled into RFP-030 on 07.31.26. Each of those suppliers has to be under contract early enough to hand over a layout. • Second-largest subcontract at $1,278,460 • Coordination hub — five other packages embed work in this concrete • Carries the 07.31.26 rulings on trench drains and athletic equipment footings
9 | 3 — next 90 work days | RFP-022 | 32-7650-10000 | Synthetic Turf Sports Field | CG&B Enterprises | 1139000 | Made-to-order turf system | Sports Field Base | 2027-05-03 | 20 | 15 | 70 | 15 | 120 | judgment | 2026-11-02 | 2026-11-16 | 71 | SCHEDULE GAP. ID 39 submits Sports Field Product Data (20 d) and then nothing -- there is no procurement activity for $1,139,000 of turf. Matrix Helix 46 oz with Elia infill over a SOTERIA 20mm pad is manufactured to order; 70 working days after approval is the estimate used here and it should be confirmed with the manufacturer before this ranking is relied on. • $1,139,000 with no procurement activity anywhere in the schedule • Made-to-order product; a late release cannot be recovered by adding crews • OPEN: Sprinturf's bid never split between RFP-016 and RFP-022
10 | 3 — next 90 work days | RFP-094 | 12-7340-10000 | Bleachers & Press Box | California Bleachers (Nata Construction) | 400879.4 | Bleacher and press box fabrication | Bleacher Installation | 2027-04-19 | 40 | 15 | 40 | 15 | 110 | sched | 2026-11-02 | 2026-11-16 | 71 | IDs 38/59/79. Two chains that look similar and are not: the product ships in time for a 4/19/27 install, but the ANCHOR LAYOUT has to reach RFP-030 by 3/8/27 for the footings, and it comes out of a deferred submittal that goes to the AHJ, not just the EOR. • Deferred submittal — delegated design through the AHJ • OPEN: the only specifications that exist are the written blocks on sheet A1-40 • Anchor layout feeds RFP-030's footings a month before fabrication would suggest
11 | 3 — next 90 work days | ITB-056 | 08-1000-10000 | Doors, Frames & Hardware | All 5's Construction | 43186 | Hollow metal frames — set in CMU | Erect CMU | 2027-04-05 | 20 | 15 | 50 | 15 | 100 | sched | 2026-11-02 | 2026-11-16 | 71 | IDs 21/56/77 for frames, 26/61/86 for doors. Buying this package to the 8/17/27 door install misses by five months -- the FRAMES are what bind, and they have to be on site for masonry. • Frames, not doors, are the driver — the buy-out date is CMU, not door install • OPEN: Door 106 panic hardware ambiguity, shared with ITB-054, life-safety
12 | 3 — next 90 work days | RFP-023 | 32-7100-10000 | Fencing & Gates | Tahoe Fence Co | 240789 | Fence and gate fabrication | Fence Posts | 2027-03-08 | 15 | 15 | 30 | 15 | 75 | judgment | 2026-11-09 | 2026-11-23 | 76 | SCHEDULE GAP -- no submittal or procurement activity for fencing. This is also the only package whose scope-review record on file is a blank template, so there is no evidence the scope review was ever held. • OPEN: the scope review agenda on file is a blank template — no evidence the scope review was ever held
13 | 3 — next 90 work days | RFP-098 | 22-1000-10000 | Plumbing Systems | US Mechanical | 428546 | Plumbing rough-in material | Rough-in Underground Plumbing | 2027-03-01 | 15 | 15 | 15 | 15 | 60 | sched | 2026-11-23 | 2026-12-07 | 86 | IDs 32/53/75 and 33/64/85. The underground rough-in is what binds.
14 | 3 — next 90 work days | RFP-016 | 32-8000-10000 | Landscaping & Irrigation | Black Canyon Construction | 350200 | Irrigation mainline sleeving ahead of curb and paving | Concrete Curbing | 2027-03-08 | 15 | 15 | 20 | 15 | 65 | judgment | 2026-11-23 | 2026-12-07 | 86 | SCHEDULE GAP -- landscaping and irrigation appear in no procurement and no field activity. Sleeving is the early obligation; planting is late. This package also carries the shot put and discus mix ruled to RFP-016 on 08.06.26 (A5), which RFP-030 and ITB-019 have to coordinate around. • OPEN AND BLOCKING: the GMP carries Black Canyon at $350,200 but their proposal on file states $111,275 — a 3.1x delta that must be reconciled before this issues
15 | 3 — next 90 work days | RFP-031 | 04-1000-10000 | Masonry | Henderson Masonry | 189449 | CMU | Erect CMU | 2027-04-05 | 15 | 15 | 40 | 15 | 85 | sched | 2026-11-23 | 2026-12-07 | 86 | IDs 36/55/72 and 23/50/69. Hollow metal frames from ITB-056 are set in this masonry, so ITB-056's frame chain has to beat the same 4/5/27 date.
16 | 4 — scheduled | RFP-100 | 23-8000-10000 | HVAC & Building Control Systems (incl. Test & Balance) | US Mechanical | 265565 | Mechanical equipment | Set Mechanical Equipment | 2027-07-13 | 40 | 15 | 80 | 15 | 150 | sched | 2026-12-01 | 2026-12-15 | 92 | IDs 27/51/74 and 28/62/83. Test & Balance sits inside this package per the 08.06.26 A7 ruling and runs 8/24-9/7/27, after the field is complete.
17 | 4 — scheduled | ITB-019 | 32-7605-10000 / 32-7610-10000 / 32-7615-10000 | Track & Field Athletic Equipment | Exerplay | 307090 | Equipment sleeves and anchors — embedded by RFP-030 | Sports Equipment Sleeves | 2027-04-26 | 20 | 15 | 40 | 15 | 90 | judgment | 2026-12-07 | 2026-12-21 | 96 | SCHEDULE GAP -- no procurement activity for athletic equipment. The equipment installs 7/13/27, but the SLEEVES are embedded in RFP-030's concrete on 4/26/27. Buying this package to the install date strands the concrete sub. • Sleeves are embedded by another sub four months before this sub installs • OPEN: 12 93 00 is claimed by both ITB-018 and ITB-019 • Exerplay carries four GMP lines across two packages — they must split cleanly
18 | 4 — scheduled | ITB-078 | 10-3050-10000 | Flagpoles | YESCO | 11596.67 | Foundation and sleeve detail to RFP-030 | Concrete Curbing | 2027-03-08 | 15 | 15 | 0 | 15 | 45 | judgment | 2026-12-21 | 2027-01-04 | 106 | Small money, early dependency: the foundation is RFP-030's pour and needs this supplier's base detail long before the pole shows up.
19 | 4 — scheduled | RFP-109 | 12-7400-10000 | Prefabricated Ticket Booth | Porta-King Building Systems | 27019.32 | Prefabricated building, factory built to order | Press Box Installation window | 2027-06-01 | 20 | 15 | 50 | 15 | 100 | judgment | 2026-12-29 | 2027-01-12 | 112 | SCHEDULE GAP -- the ticket booth appears in no procurement and no field activity. It is a manufactured building (Porta-King DURASTEEL PC64 per the 08.04.26 ruling), not a delivered product, and its pad is RFP-030's. • Manufactured building with no schedule activity of any kind
20 | 4 — scheduled | RFP-021 | 32-7620-10000 | Running Track Surfacing | Elite Sports Builders | 450741 | Track surfacing materials | Running Track Base | 2027-06-01 | 20 | 15 | 40 | 15 | 90 | judgment | 2027-01-12 | 2027-01-26 | 122 | SCHEDULE GAP -- no procurement line for track surfacing. Surfacing runs 7/13-7/26/27 and Sports Field Substantial Completion is 7/26/27: zero float to a contractual milestone, on a temperature-dependent application in a high-desert July, with only two real bidders behind it. • ZERO float — surfacing finishes the same day the field is contractually complete • Weather-dependent application in July at 6,000 ft • Only two real bidders; no recovery by rebidding
21 | 4 — scheduled | ITB-054 | 08-3050-10000 | Special Doors | Crawford Door Sales of NV | 31214 | Coiling door fabrication | Windows & Coiling Doors | 2027-06-15 | 20 | 15 | 45 | 15 | 95 | judgment | 2027-01-19 | 2027-02-02 | 127 | SCHEDULE GAP -- special doors have no procurement activity. The Door 106 panic hardware ambiguity is shared with ITB-056 and is a life-safety item.
22 | 4 — scheduled | RFP-060 | 09-2000-10000 | Framing, Drywall & Painting (incl. FRP) | Jetstream Construction | 266211 | Framing and sheathing materials | Exterior Framing & Sheathing | 2027-05-24 | 15 | 15 | 20 | 15 | 65 | judgment | 2027-02-08 | 2027-02-22 | 141 | One agreement carrying four exhibits per the 08.06.26 D ruling -- RFP-060 plus ITB-044, ITB-062 and ITB-077. None of the four can issue until all four are drafted, so this release date is really the earliest of that whole group. • One agreement, four exhibits (RFP-060, ITB-044, ITB-062, ITB-077) — none can issue until all four are drafted • ITB-044 and ITB-062 are carried at $0; their money is inside RFP-060's $266,211
23 | 4 — scheduled | ITB-077 | 10-3120-10000 | Lockers | Jetstream Construction | 20566 | Locker fabrication — ASI Pro Collection | Doors & Hardware | 2027-08-17 | 20 | 15 | 40 | 15 | 90 | judgment | 2027-02-08 | 2027-02-22 | 141 | Inside the Jetstream agreement with RFP-060. No spec section was ever issued; the basis of design is Clarification No. 1 RFI #3. PULLED FORWARD from 2027-04-13 to 2027-02-22: this exhibit is part of Jetstream — one agreement, four exhibits (PM ruling 08.06.26 D), and the agreement cannot issue until every exhibit attached to it is finished.
24 | 4 — scheduled | ITB-044 | — | Insulation | Jetstream Construction | 0 | Insulation materials | Insulation | 2027-06-22 | 10 | 10 | 15 | 15 | 50 | judgment | 2027-02-08 | 2027-02-22 | 141 | Carried at $0 in the GMP -- '(SEE LINE #060)'. No separate money; releases inside the Jetstream agreement. PULLED FORWARD from 2027-04-13 to 2027-02-22: this exhibit is part of Jetstream — one agreement, four exhibits (PM ruling 08.06.26 D), and the agreement cannot issue until every exhibit attached to it is finished.
25 | 4 — scheduled | ITB-062 | — | Acoustical Ceiling Treatments | Jetstream Construction | 0 | Ceiling grid and tile | MEP Trim | 2027-07-20 | 15 | 15 | 30 | 15 | 75 | judgment | 2027-02-08 | 2027-02-22 | 141 | Carried at $0 in the GMP -- '(SEE LINE #060)'. No separate money; releases inside the Jetstream agreement. PULLED FORWARD from 2027-04-06 to 2027-02-22: this exhibit is part of Jetstream — one agreement, four exhibits (PM ruling 08.06.26 D), and the agreement cannot issue until every exhibit attached to it is finished.
26 | 4 — scheduled | ITB-085 | 11-0080-10000 | Warming Kitchen Food Service Equipment | RESCO | 35950 | Equipment delivery | Casework | 2027-07-13 | 20 | 15 | 40 | 15 | 90 | judgment | 2027-02-23 | 2027-03-09 | 152 | SCHEDULE GAP. The equipment lands late, but RFP-098/100/103 cannot rough in walls without approved cut sheets -- the submittal is the early obligation, not the delivery.
27 | 4 — scheduled | ITB-040 | 07-1000-10000 | Moisture Protection & Sealants (incl. Acoustical Caulking) | Western Sealants | 15500 | Sealant and weather barrier materials | Roof, Fascia, Soffit Panels | 2027-06-08 | 15 | 10 | 15 | 15 | 55 | judgment | 2027-03-09 | 2027-03-23 | 162 | Below-grade waterproofing only per the 07.31.26 ruling. 07 25 00 Weather Barriers is shared with RFP-045 along that same boundary.
28 | 4 — scheduled | ITB-074 | 10-2020-10000 | Building & Fire Protection Specialties | Henri | 38852 | In-wall backing coordination with RFP-060 | Framing | 2027-06-01 | 15 | 15 | 0 | 15 | 45 | judgment | 2027-03-16 | 2027-03-30 | 167 | The accessories install late but their backing goes in during framing, so the layout is the early obligation. Carries the fire protection cabinets and the wall and door protection per the 08.06.26 D and A3 rulings.
29 | 4 — scheduled | ITB-018 | 32-7600-10000 | Site Furnishings | Exerplay | 17221 | Site furnishings supply for ITB-019 to install | Sports Field Equipment Install | 2027-07-13 | 15 | 15 | 30 | 15 | 75 | judgment | 2027-03-16 | 2027-03-30 | 167 | Supply only per the 08.06.26 A2 ruling -- ITB-019 installs. Same vendor as ITB-019, so both exhibits should travel together.
30 | 4 — scheduled | ITB-072 | 10-3070-10000 | Building Signage | YESCO | 22450 | Sign fabrication | Exterior Finishes Complete | 2027-07-19 | 15 | 10 | 30 | 15 | 70 | judgment | 2027-03-29 | 2027-04-12 | 176 | Same vendor as ITB-078 and ITB-089 (YESCO) -- three exhibits, one contract negotiation.
31 | 4 — scheduled | ITB-071 | 10-1020-10000 | Visual Display Boards & Menu Display Case | ADP Lemco | 6695.82 | Boards and display case fabrication | Casework | 2027-07-13 | 15 | 10 | 25 | 15 | 65 | judgment | 2027-03-30 | 2027-04-13 | 177 | The 'ADD Menu Display Case' alternate is worded identically in ITB-072 and ITB-085, and this package's own title names it -- three packages may be touching one item.
32 | 4 — scheduled | ITB-067 | 09-8100-10000 | Concrete Finishing | Ryerson Concrete | 35993 | Sealed concrete materials | Flooring | 2027-08-03 | 10 | 10 | 15 | 15 | 50 | judgment | 2027-05-11 | 2027-05-25 | 207 | Scope grew when ITB-066 was VE'd out -- those locations became sealed concrete under this package per the 08.04.26 ruling.
33 | 4 — scheduled | ITB-070 | 50-1000-10000 | Final Cleaning | Cleaning Services Inc. | 5226 | Labor only | Construction Clean | 2027-08-24 | 5 | 5 | 0 | 15 | 25 | judgment | 2027-07-06 | 2027-07-20 | 247 | No scope narrative was ever issued (08.06.26 E1 ruling) -- the exhibit has to be drafted from the four proposals on hand. • No scope narrative was ever issued — the exhibit is drafted from proposals
| — not released (scope removed) | ITB-066 | — | Fluid-Applied Flooring | — | 0 |  | — not released |  | 0 | 0 | 0 | 15 | 0 | n/a |  |  |  | Scope removed by the Owner in a value engineering exercise, 08.04.26. No subcontract will be issued. Those locations became sealed concrete under ITB-067. • Scope removed by the Owner. No subcontract.

## buyout log
Package | List | Title | Carried Subcontractor | Phase Code | Carried Value | GMP Lines Carried (BackSheet) | Group (agreement or shared vendor) | Group Releases By | Attachment A | Cover Sheet | Subcontract | Executed | NTP | Attachment A Draft By | Latest Release Date | Field Need Date | Rank
RFP-033 | 1% (NRS 338.16995) | Structural Steel & Ornamental Metals | Corona Steel | 05-1000-10000 | 166281 | #026 Site Metals — (SEE LINE #033) $0; #033 Structural Steel & Ornamental Metals — Corona Steel $166,281 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-08-24 | 2026-09-07 | 2027-05-03 | 1
RFP-103 | 1% (NRS 338.16995) | Electrical & Low Voltage Systems (incl. Sports Field Lighting) | Quantum Electric | 26-1000-10000 | 1074541 | #103 Electrical & Low Voltage Systems — Quantum Electric $1,074,541; #105 Specialty Low Voltage Systems - With Scope #103 $0; #106 Electronic Safety & Security Systems - With Scope #103 $0; #107 Sports Field Lighting — (SEE LINE #103) $0 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-09-01 | 2026-09-15 | 2027-07-06 | 2
RFP-002 | 1% (NRS 338.16995) | Abatement & Building Wrecking | Northstar Contracting Group | 02-1110-10000 | 741912 | #002 Abatement & Building Wrecking — Northstar Contracting Group $741,912; #004 Building Wrecking — (SEE LINE #002) $0 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-09-15 | 2026-09-29 | 2026-11-24 | 3
ITB-008 | Non-1% (ITB) | Surveying, Layout & Staking | Prewitt Land Surveying | 02-1010-10000 | 80767.5 | #007 Horizontal Survey & Staking — Prewitt Land Surveying $80,768 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-09-29 | 2026-10-13 | 2026-11-24 | 4
ITB-089 | Non-1% (ITB) | Scoreboards | YESCO | 11-0101-10000 | 99483 | #089 Scoreboard — YESCO $99,483 | YESCO — signage, flagpoles and scoreboard | 2026-10-19 | DRAFTED — with PM |  | not issued |  |  | 2026-10-05 | 2026-10-19 | 2027-03-08 | 5
RFP-008 | 1% (NRS 338.16995) | Site Demolition, Salvage, Earthwork, Asphalt Paving, Wet Utilities, & Site Signage & Striping | TAB Contractors (New-Com) | 31-2000-10000 | 1741321 | #008 Site Demo, Earthwork, Paving & Wet Utilities — TAB Contractors (New-Com) $1,741,321; #009 Utilities — (SEE LINE #008) $0; #014 Asphalt Paving - See Scope #008 $0; #015 Site Signage, Striping, & Parking Accessories — (SEE LINE #008) $0 |  |  | DRAFTED — with PM | BUILT | not issued |  |  | 2026-10-06 | 2026-10-20 | 2026-11-24 | 6
RFP-045 | 1% (NRS 338.16995) | Metal Roofing, Fascia & Soffit Panels | Foursquare Roof and Walls | 07-4100-10000 | 142585 | #045 Metal Roofing, Fascia & Soffit Panels — Foursquare Roof and Walls $142,585; #049 Metal Panels — (SEE LINE #045) $0 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-10-13 | 2026-10-27 | 2027-06-08 | 7
RFP-030 | 1% (NRS 338.16995) | Concrete | Sahara Concrete | 03-1000-10000 | 1278459.84 | #024 Site Concrete — (SEE LINE #030) $0; #030 Concrete — Sahara Concrete $1,278,460 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-11-02 | 2026-11-16 | 2027-02-08 | 8
RFP-022 | 1% (NRS 338.16995) | Synthetic Turf Sports Field | CG&B Enterprises | 32-7650-10000 | 1139000 | #022 Synthetic Turf Sports Field — CG&B Enterprises $1,139,000 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-11-02 | 2026-11-16 | 2027-05-03 | 9
RFP-094 | 1% (NRS 338.16995) | Bleachers & Press Box | California Bleachers (Nata Construction) | 12-7340-10000 | 400879.4 | #094 Bleachers & Press Box (SUPPLY) — California Bleachers (Nata Construction) $400,879 |  |  | not started |  | not issued |  |  | 2026-11-02 | 2026-11-16 | 2027-04-19 | 10
ITB-056 | Non-1% (ITB) | Doors, Frames & Hardware | All 5's Construction | 08-1000-10000 | 43186 | #056 Doors, Frames, & Hardware — All 5's Construction $43,186; #057 Doors, Frames, & Hardware (Install) - See Scope #056 $0 |  |  | not started |  | not issued |  |  | 2026-11-02 | 2026-11-16 | 2027-04-05 | 11
RFP-023 | 1% (NRS 338.16995) | Fencing & Gates | Tahoe Fence Co | 32-7100-10000 | 240789 | #023 Fencing & Gates — Tahoe Fence Co $240,789 |  |  | not started |  | not issued |  |  | 2026-11-09 | 2026-11-23 | 2027-03-08 | 12
RFP-098 | 1% (NRS 338.16995) | Plumbing Systems | US Mechanical | 22-1000-10000 | 428546 | #098 Plumbing Systems — US Mechanical $428,546 | US Mechanical — plumbing and HVAC | 2026-12-07 | not started |  | not issued |  |  | 2026-11-23 | 2026-12-07 | 2027-03-01 | 13
RFP-016 | 1% (NRS 338.16995) | Landscaping & Irrigation | Black Canyon Construction | 32-8000-10000 | 350200 | #016 Landscape & Irrigation — Black Canyon Construction $350,200 |  |  | not started |  | not issued |  |  | 2026-11-23 | 2026-12-07 | 2027-03-08 | 14
RFP-031 | 1% (NRS 338.16995) | Masonry | Henderson Masonry | 04-1000-10000 | 189449 | #031 Masonry — Henderson Masonry $189,449 |  |  | DRAFTED — with PM |  | not issued |  |  | 2026-11-23 | 2026-12-07 | 2027-04-05 | 15
RFP-100 | 1% (NRS 338.16995) | HVAC & Building Control Systems (incl. Test & Balance) | US Mechanical | 23-8000-10000 | 265565 | #100 HVAC Systems — US Mechanical $265,565; #101 Building Controls - With Scope #100 $0; #102 Test & Balance - With Scope #100 — (SEE LINE #100) $0 | US Mechanical — plumbing and HVAC | 2026-12-07 | not started |  | not issued |  |  | 2026-12-01 | 2026-12-15 | 2027-07-13 | 16
ITB-019 | Non-1% (ITB) | Track & Field Athletic Equipment | Exerplay | 32-7605-10000 / 32-7610-10000 / 32-7615-10000 | 307090 | #018 Track & Field Equipment (SUPPLY) — Exerplay $156,973; #019 Track Equipment (INSTALL) — Exerplay $109,237; #020 Field Equipment (INSTALL) — Exerplay $40,880 | Exerplay — supplies ITB-018, supplies and installs ITB-019 | 2026-12-21 | not started |  | not issued |  |  | 2026-12-07 | 2026-12-21 | 2027-04-26 | 17
ITB-078 | Non-1% (ITB) | Flagpoles | YESCO | 10-3050-10000 | 11596.67 | #078 Flagpoles — YESCO $11,597 | YESCO — signage, flagpoles and scoreboard | 2026-10-19 | not started |  | not issued |  |  | 2026-12-21 | 2027-01-04 | 2027-03-08 | 18
RFP-109 | 1% (NRS 338.16995) | Prefabricated Ticket Booth | Porta-King Building Systems | 12-7400-10000 | 27019.32 | #109 Prefabricated Ticket Booth — Porta-King Building Systems $27,019 |  |  | not started |  | not issued |  |  | 2026-12-29 | 2027-01-12 | 2027-06-01 | 19
RFP-021 | 1% (NRS 338.16995) | Running Track Surfacing | Elite Sports Builders | 32-7620-10000 | 450741 | #021 Running Track Surfacing — Elite Sports Builders $450,741 |  |  | not started |  | not issued |  |  | 2027-01-12 | 2027-01-26 | 2027-06-01 | 20
ITB-054 | Non-1% (ITB) | Special Doors | Crawford Door Sales of NV | 08-3050-10000 | 31214 | #054 Special Doors — Crawford Door Sales of NV $31,214 |  |  | not started |  | not issued |  |  | 2027-01-19 | 2027-02-02 | 2027-06-15 | 21
RFP-060 | 1% (NRS 338.16995) | Framing, Drywall & Painting (incl. FRP) | Jetstream Construction | 09-2000-10000 | 266211 | #060 Framing, Drywall & Painting — Jetstream Construction $266,211 | Jetstream — one agreement, four exhibits (PM ruling 08.06.26 D) | 2027-02-22 | not started |  | not issued |  |  | 2027-02-08 | 2027-02-22 | 2027-05-24 | 22
ITB-077 | Non-1% (ITB) | Lockers | Jetstream Construction | 10-3120-10000 | 20566 | #077 Lockers — Jetstream Construction $20,566 | Jetstream — one agreement, four exhibits (PM ruling 08.06.26 D) | 2027-02-22 | not started |  | not issued |  |  | 2027-02-08 | 2027-02-22 | 2027-08-17 | 23
ITB-044 | Non-1% (ITB) | Insulation | Jetstream Construction | — | 0 | #044 Insulation — (SEE LINE #060) $0 | Jetstream — one agreement, four exhibits (PM ruling 08.06.26 D) | 2027-02-22 | not started |  | not issued |  |  | 2027-02-08 | 2027-02-22 | 2027-06-22 | 24
ITB-062 | Non-1% (ITB) | Acoustical Ceiling Treatments | Jetstream Construction | — | 0 | #062 Acoustical Ceiling Treatments — (SEE LINE #060) $0 | Jetstream — one agreement, four exhibits (PM ruling 08.06.26 D) | 2027-02-22 | not started |  | not issued |  |  | 2027-02-08 | 2027-02-22 | 2027-07-20 | 25
ITB-085 | Non-1% (ITB) | Warming Kitchen Food Service Equipment | RESCO | 11-0080-10000 | 35950 | #085 Warming Kitchen Foodservice Equipment — RESCO $35,950 |  |  | not started |  | not issued |  |  | 2027-02-23 | 2027-03-09 | 2027-07-13 | 26
ITB-040 | Non-1% (ITB) | Moisture Protection & Sealants (incl. Acoustical Caulking) | Western Sealants | 07-1000-10000 | 15500 | #040 Moisture Protection & Sealants — Western Sealants $15,500 |  |  | not started |  | not issued |  |  | 2027-03-09 | 2027-03-23 | 2027-06-08 | 27
ITB-074 | Non-1% (ITB) | Building & Fire Protection Specialties | Henri | 10-2020-10000 | 38852 | #074 Building & Fire Protection Accessories — Henri $38,852; #075 Fire Protection Specialties — (SEE LINE #074) $0 |  |  | not started |  | not issued |  |  | 2027-03-16 | 2027-03-30 | 2027-06-01 | 28
ITB-018 | Non-1% (ITB) | Site Furnishings | Exerplay | 32-7600-10000 | 17221 | #017 Site Furnishings — Exerplay $17,221 | Exerplay — supplies ITB-018, supplies and installs ITB-019 | 2026-12-21 | not started |  | not issued |  |  | 2027-03-16 | 2027-03-30 | 2027-07-13 | 29
ITB-072 | Non-1% (ITB) | Building Signage | YESCO | 10-3070-10000 | 22450 | #072 Building Signage — YESCO $22,450 | YESCO — signage, flagpoles and scoreboard | 2026-10-19 | DRAFTED — with PM |  | not issued |  |  | 2027-03-29 | 2027-04-12 | 2027-07-19 | 30
ITB-071 | Non-1% (ITB) | Visual Display Boards & Menu Display Case | ADP Lemco | 10-1020-10000 | 6695.82 | #071 Visual Display Boards — ADP Lemco $6,696; #083 Manufactured Specialties — (SEE LINE #071) $0 |  |  | not started |  | not issued |  |  | 2027-03-30 | 2027-04-13 | 2027-07-13 | 31
ITB-067 | Non-1% (ITB) | Concrete Finishing | Ryerson Concrete | 09-8100-10000 | 35993 | #067 Concrete Finishing — Ryerson Concrete $35,993 |  |  | not started |  | not issued |  |  | 2027-05-11 | 2027-05-25 | 2027-08-03 | 32
ITB-070 | Non-1% (ITB) | Final Cleaning | Cleaning Services Inc. | 50-1000-10000 | 5226 | #070 Progressive & Final Clean Requirements — Cleaning Services Inc. $5,226 |  |  | not started |  | not issued |  |  | 2027-07-06 | 2027-07-20 | 2027-08-24 | 33
ITB-066 | Non-1% (ITB) | Fluid-Applied Flooring | — | — | 0 | #066 Fluid-Applied Flooring $0 |  |  | not started |  | not issued
|  |  |  | TOTAL CARRIED | 9675290.55

## long-lead chains
Rank | Package | Binding? | Long-Lead Chain | Field Activity It Serves | Field Need Date | Submit | Review | Procure | Exec | Total | Duration Basis | Release By | Work Days of Slack
1 | RFP-033 | BINDING | Joist & deck — deferred submittal | Steel, Joists, & Deck Erection | 2027-05-03 | 40 | 15 | 100 | 15 | 170 | sched | 2026-09-07 | 21
1 | RFP-033 | float | Structural steel | Steel, Joists, & Deck Erection | 2027-05-03 | 40 | 30 | 80 | 15 | 165 | sched | 2026-09-14 | 26
1 | RFP-033 | float | Anchor bolts — embedded by RFP-030 | Foundations | 2027-02-15 | 15 | 15 | 15 | 15 | 60 | sched | 2026-11-23 | 76
2 | RFP-103 | BINDING | Electrical lighting package | Set Electrical Equipment | 2027-07-06 | 40 | 15 | 140 | 15 | 210 | sched | 2026-09-15 | 27
2 | RFP-103 | float | Musco light fixtures | Install Musco Light Poles | 2027-03-08 | 10 | 15 | 50 | 15 | 90 | sched | 2026-11-02 | 61
2 | RFP-103 | float | Electrical rough-in material | UG Electrical & Musco Bases | 2027-02-08 | 15 | 15 | 15 | 15 | 60 | sched | 2026-11-16 | 71
3 | RFP-002 | BINDING | NESHAP/NDEP notification and abatement work plan | Abatement ahead of Demo | 2026-11-24 | 15 | 10 | 0 | 15 | 40 | judgment | 2026-09-29 | 37
4 | ITB-008 | BINDING | Survey control and staking | Temp Fence & Mobilize | 2026-11-24 | 10 | 5 | 0 | 15 | 30 | judgment | 2026-10-13 | 47
5 | ITB-089 | BINDING | Deferred structural submittal and fabrication | Install Musco Light Poles | 2027-03-08 | 30 | 15 | 40 | 15 | 100 | judgment | 2026-10-19 | 51
6 | RFP-008 | BINDING | Mobilization — first sub on the field | Temp Fence & Mobilize | 2026-11-24 | 10 | 0 | 0 | 15 | 25 | judgment | 2026-10-20 | 52
6 | RFP-008 | float | Underground utility materials | Storm Drain | 2027-02-08 | 15 | 15 | 15 | 15 | 60 | sched | 2026-11-16 | 71
7 | RFP-045 | BINDING | Metal panels | Roof, Fascia, Soffit Panels | 2027-06-08 | 30 | 15 | 100 | 15 | 160 | sched | 2026-10-27 | 57
7 | RFP-045 | float | Roof materials | Roof, Fascia, Soffit Panels | 2027-06-08 | 20 | 15 | 100 | 15 | 150 | sched | 2026-11-10 | 67
8 | RFP-030 | BINDING | Footing rebar | Retaining Walls / Build Building Pad | 2027-02-08 | 15 | 15 | 15 | 15 | 60 | sched | 2026-11-16 | 71
8 | RFP-030 | float | Anchor bolt and embed coordination from RFP-033 | Foundations | 2027-02-15 | 15 | 15 | 15 | 15 | 60 | sched | 2026-11-23 | 76
9 | RFP-022 | BINDING | Made-to-order turf system | Sports Field Base | 2027-05-03 | 20 | 15 | 70 | 15 | 120 | judgment | 2026-11-16 | 71
10 | RFP-094 | BINDING | Bleacher and press box fabrication | Bleacher Installation | 2027-04-19 | 40 | 15 | 40 | 15 | 110 | sched | 2026-11-16 | 71
10 | RFP-094 | float | Anchor layout to RFP-030 — deferred structural submittal | Bleacher Footings | 2027-03-08 | 40 | 15 | 0 | 15 | 70 | sched | 2026-11-30 | 81
11 | ITB-056 | BINDING | Hollow metal frames — set in CMU | Erect CMU | 2027-04-05 | 20 | 15 | 50 | 15 | 100 | sched | 2026-11-16 | 71
11 | ITB-056 | float | Doors and hardware | Doors & Hardware | 2027-08-17 | 40 | 20 | 100 | 15 | 175 | sched | 2026-12-15 | 92
12 | RFP-023 | BINDING | Fence and gate fabrication | Fence Posts | 2027-03-08 | 15 | 15 | 30 | 15 | 75 | judgment | 2026-11-23 | 76
13 | RFP-098 | BINDING | Plumbing rough-in material | Rough-in Underground Plumbing | 2027-03-01 | 15 | 15 | 15 | 15 | 60 | sched | 2026-12-07 | 86
13 | RFP-098 | float | Plumbing equipment and fixtures | MEP Trim | 2027-07-20 | 40 | 15 | 60 | 15 | 130 | sched | 2027-01-19 | 117
14 | RFP-016 | BINDING | Irrigation mainline sleeving ahead of curb and paving | Concrete Curbing | 2027-03-08 | 15 | 15 | 20 | 15 | 65 | judgment | 2026-12-07 | 86
14 | RFP-016 | float | Planting and turf-area finish materials | Sports Field Base | 2027-05-03 | 15 | 15 | 20 | 15 | 65 | judgment | 2027-02-01 | 126
15 | RFP-031 | BINDING | CMU | Erect CMU | 2027-04-05 | 15 | 15 | 40 | 15 | 85 | sched | 2026-12-07 | 86
15 | RFP-031 | float | Masonry rebar | Erect CMU | 2027-04-05 | 15 | 15 | 15 | 15 | 60 | sched | 2027-01-11 | 111
16 | RFP-100 | BINDING | Mechanical equipment | Set Mechanical Equipment | 2027-07-13 | 40 | 15 | 80 | 15 | 150 | sched | 2026-12-15 | 92
16 | RFP-100 | float | Mechanical rough-in material | MEP Overhead Rough | 2027-05-24 | 15 | 15 | 15 | 15 | 60 | sched | 2027-03-01 | 146
17 | ITB-019 | BINDING | Equipment sleeves and anchors — embedded by RFP-030 | Sports Equipment Sleeves | 2027-04-26 | 20 | 15 | 40 | 15 | 90 | judgment | 2026-12-21 | 96
17 | ITB-019 | float | Athletic equipment | Sports Field Equipment Install | 2027-07-13 | 20 | 15 | 40 | 15 | 90 | judgment | 2027-03-09 | 152
18 | ITB-078 | BINDING | Foundation and sleeve detail to RFP-030 | Concrete Curbing | 2027-03-08 | 15 | 15 | 0 | 15 | 45 | judgment | 2027-01-04 | 106
18 | ITB-078 | float | Flagpole delivery | Exterior Finishes Complete | 2027-07-19 | 15 | 15 | 30 | 15 | 75 | judgment | 2027-04-05 | 171
19 | RFP-109 | BINDING | Prefabricated building, factory built to order | Press Box Installation window | 2027-06-01 | 20 | 15 | 50 | 15 | 100 | judgment | 2027-01-12 | 112
20 | RFP-021 | BINDING | Track surfacing materials | Running Track Base | 2027-06-01 | 20 | 15 | 40 | 15 | 90 | judgment | 2027-01-26 | 122
21 | ITB-054 | BINDING | Coiling door fabrication | Windows & Coiling Doors | 2027-06-15 | 20 | 15 | 45 | 15 | 95 | judgment | 2027-02-02 | 127
22 | RFP-060 | BINDING | Framing and sheathing materials | Exterior Framing & Sheathing | 2027-05-24 | 15 | 15 | 20 | 15 | 65 | judgment | 2027-02-22 | 141
23 | ITB-077 | BINDING | Locker fabrication — ASI Pro Collection | Doors & Hardware | 2027-08-17 | 20 | 15 | 40 | 15 | 90 | judgment | 2027-04-13 | 177
24 | ITB-044 | BINDING | Insulation materials | Insulation | 2027-06-22 | 10 | 10 | 15 | 15 | 50 | judgment | 2027-04-13 | 177
25 | ITB-062 | BINDING | Ceiling grid and tile | MEP Trim | 2027-07-20 | 15 | 15 | 30 | 15 | 75 | judgment | 2027-04-06 | 172
26 | ITB-085 | BINDING | Equipment delivery | Casework | 2027-07-13 | 20 | 15 | 40 | 15 | 90 | judgment | 2027-03-09 | 152
26 | ITB-085 | float | Approved equipment cut sheets set the MEP rough-in | MEP Rough In Walls | 2027-06-08 | 20 | 15 | 0 | 15 | 50 | judgment | 2027-03-30 | 167
27 | ITB-040 | BINDING | Sealant and weather barrier materials | Roof, Fascia, Soffit Panels | 2027-06-08 | 15 | 10 | 15 | 15 | 55 | judgment | 2027-03-23 | 162
28 | ITB-074 | BINDING | In-wall backing coordination with RFP-060 | Framing | 2027-06-01 | 15 | 15 | 0 | 15 | 45 | judgment | 2027-03-30 | 167
28 | ITB-074 | float | Specialties and fire protection cabinets | MEP Trim | 2027-07-20 | 15 | 15 | 30 | 15 | 75 | judgment | 2027-04-06 | 172
29 | ITB-018 | BINDING | Site furnishings supply for ITB-019 to install | Sports Field Equipment Install | 2027-07-13 | 15 | 15 | 30 | 15 | 75 | judgment | 2027-03-30 | 167
30 | ITB-072 | BINDING | Sign fabrication | Exterior Finishes Complete | 2027-07-19 | 15 | 10 | 30 | 15 | 70 | judgment | 2027-04-12 | 176
31 | ITB-071 | BINDING | Boards and display case fabrication | Casework | 2027-07-13 | 15 | 10 | 25 | 15 | 65 | judgment | 2027-04-13 | 177
32 | ITB-067 | BINDING | Sealed concrete materials | Flooring | 2027-08-03 | 10 | 10 | 15 | 15 | 50 | judgment | 2027-05-25 | 207
33 | ITB-070 | BINDING | Labor only | Construction Clean | 2027-08-24 | 5 | 5 | 0 | 15 | 25 | judgment | 2027-07-20 | 247

## blocking items
Rank | Package | Carried Subcontractor | Open Item / Risk | Source
1 | RFP-033 | Corona Steel | Longest submittal review on the job (30 d) with no slack behind it | buy-out analysis
1 | RFP-033 | Corona Steel | Delegated design: joist & deck is a deferred submittal | buy-out analysis
1 | RFP-033 | Corona Steel | OPEN: goal post structural design is listed as a deferred submittal on G0-00 and is assigned to no package | buy-out analysis
2 | RFP-103 | Quantum Electric | Largest subcontract on the job at $1,074,541 | buy-out analysis
2 | RFP-103 | Quantum Electric | Longest procurement on the job (140 d) and it defines Material Procurement Complete | buy-out analysis
2 | RFP-103 | Quantum Electric | Delegated design: Musco pole foundations and sports lighting photometrics | buy-out analysis
2 | RFP-103 | Quantum Electric | Single-source manufacturer (Musco) — no recovery by rebidding | buy-out analysis
2 | RFP-103 | Quantum Electric | OPEN: the ASI formalizing the no-fire-alarm direction has not issued; the GMP Exclusion covers the money but not the drawings | buy-out analysis
3 | RFP-002 | Northstar Contracting Group | Regulatory lead, not material lead — notification periods cannot be compressed | buy-out analysis
3 | RFP-002 | Northstar Contracting Group | Asbestos: an abatement failure stops the demolition that stops everything else | buy-out analysis
3 | RFP-002 | Northstar Contracting Group | OPEN: the ES campus demolition alternate is worded identically in RFP-002 and RFP-008 and it is still unresolved whether it splits by trade | buy-out analysis
3 | RFP-002 | Northstar Contracting Group | [HIGH] SPEC-C01 02 41 00 Demolition — claimed by more than one scope doc | pm-open-items.json
3 | RFP-002 | Northstar Contracting Group | [MEDIUM] BID-P01 RFP-002 — NorthStar Contracting Group, Inc.'s price moves between documents | pm-open-items.json
3 | RFP-002 | Northstar Contracting Group | [LOW] GMP-07 Asbestos survey date differs from the staged file | pm-open-items.json
4 | ITB-008 | Prewitt Land Surveying | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
4 | ITB-008 | Prewitt Land Surveying | [MEDIUM] SPEC-N01 ITB-008 holds no spec section of its own | pm-open-items.json
5 | ITB-089 | YESCO | Deferred submittal with delegated design and no procurement activity | buy-out analysis
5 | ITB-089 | YESCO | [MEDIUM] BID-B09 YESCO bid ITB-072, ITB-078, ITB-089 as one bundled scope | pm-open-items.json
6 | RFP-008 | TAB Contractors (New-Com) | First sub on the field; every site package sequences behind it | buy-out analysis
6 | RFP-008 | TAB Contractors (New-Com) | OPEN: package title carries site signage and striping the narrative never scopes and the sub excluded twice | buy-out analysis
6 | RFP-008 | TAB Contractors (New-Com) | OPEN: accepted VE #10 at −$16,750 has no matching line in the sub's own homework | buy-out analysis
6 | RFP-008 | TAB Contractors (New-Com) | OPEN: stockpiling — narrative prohibits, GMP assumes, VE #10 relies on it | buy-out analysis
6 | RFP-008 | TAB Contractors (New-Com) | [HIGH] BID-T01 RFP-008 — Ndx LLC tabulated at a price the proposal does not state | pm-open-items.json
6 | RFP-008 | TAB Contractors (New-Com) | [HIGH] BID-T02 RFP-008 — New-Com, Inc. (TAB Contractors and MMC, Inc.) tabulated at a price the proposal does not state | pm-open-items.json
6 | RFP-008 | TAB Contractors (New-Com) | [HIGH] SPEC-C01 02 41 00 Demolition — claimed by more than one scope doc | pm-open-items.json
6 | RFP-008 | TAB Contractors (New-Com) | [MEDIUM] GMP-06 Owner Accepted Alternates supersede drawn details | pm-open-items.json
7 | RFP-045 | Foursquare Roof and Walls | OPEN: the 08.06.26 B1 ruling puts the GMP over RFI #23, reversing a written architect's answer — settle before release or the sub buys the wrong panel | buy-out analysis
7 | RFP-045 | Foursquare Roof and Walls | [HIGH] GMP-01 Berridge C-Lock in the GMP reverses RFI #23 | pm-open-items.json
8 | RFP-030 | Sahara Concrete | Second-largest subcontract at $1,278,460 | buy-out analysis
8 | RFP-030 | Sahara Concrete | Coordination hub — five other packages embed work in this concrete | buy-out analysis
8 | RFP-030 | Sahara Concrete | Carries the 07.31.26 rulings on trench drains and athletic equipment footings | buy-out analysis
8 | RFP-030 | Sahara Concrete | [MEDIUM] BID-B02 XL Concrete Masonry LLC bid RFP-030, RFP-031 as one bundled scope | pm-open-items.json
8 | RFP-030 | Sahara Concrete | [MEDIUM] GMP-06 Owner Accepted Alternates supersede drawn details | pm-open-items.json
9 | RFP-022 | CG&B Enterprises | $1,139,000 with no procurement activity anywhere in the schedule | buy-out analysis
9 | RFP-022 | CG&B Enterprises | Made-to-order product; a late release cannot be recovered by adding crews | buy-out analysis
9 | RFP-022 | CG&B Enterprises | OPEN: Sprinturf's bid never split between RFP-016 and RFP-022 | buy-out analysis
9 | RFP-022 | CG&B Enterprises | [HIGH] BID-L01 RFP-022 — Sprinturf, LLC bid this package but appears on no tab row for it | pm-open-items.json
9 | RFP-022 | CG&B Enterprises | [MEDIUM] BID-B01 Tand Inc. bid RFP-016, RFP-022 as one bundled scope | pm-open-items.json
10 | RFP-094 | California Bleachers (Nata Construction) | Deferred submittal — delegated design through the AHJ | buy-out analysis
10 | RFP-094 | California Bleachers (Nata Construction) | OPEN: the only specifications that exist are the written blocks on sheet A1-40 | buy-out analysis
10 | RFP-094 | California Bleachers (Nata Construction) | Anchor layout feeds RFP-030's footings a month before fabrication would suggest | buy-out analysis
11 | ITB-056 | All 5's Construction | Frames, not doors, are the driver — the buy-out date is CMU, not door install | buy-out analysis
11 | ITB-056 | All 5's Construction | OPEN: Door 106 panic hardware ambiguity, shared with ITB-054, life-safety | buy-out analysis
11 | ITB-056 | All 5's Construction | [HIGH] GMP-02 Door 106 panic hardware exclusion is ambiguous | pm-open-items.json
11 | ITB-056 | All 5's Construction | [MEDIUM] BID-B03 Division 09 bid ITB-044, ITB-056, ITB-062, RFP-060 as one bundled scope | pm-open-items.json
11 | ITB-056 | All 5's Construction | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
12 | RFP-023 | Tahoe Fence Co | OPEN: the scope review agenda on file is a blank template — no evidence the scope review was ever held | buy-out analysis
13 | RFP-098 | US Mechanical | [MEDIUM] BID-B04 Bombard Mechanical, LLC bid RFP-098, RFP-100 as one bundled scope | pm-open-items.json
14 | RFP-016 | Black Canyon Construction | OPEN AND BLOCKING: the GMP carries Black Canyon at $350,200 but their proposal on file states $111,275 — a 3.1x delta that must be reconciled before this issues | buy-out analysis
14 | RFP-016 | Black Canyon Construction | [HIGH] SPEC-C05 32 91 13 Shot Put and Discus Mix — claimed by more than one scope doc | pm-open-items.json
14 | RFP-016 | Black Canyon Construction | [MEDIUM] BID-B01 Tand Inc. bid RFP-016, RFP-022 as one bundled scope | pm-open-items.json
15 | RFP-031 | Henderson Masonry | [MEDIUM] BID-B02 XL Concrete Masonry LLC bid RFP-030, RFP-031 as one bundled scope | pm-open-items.json
16 | RFP-100 | US Mechanical | [MEDIUM] BID-B04 Bombard Mechanical, LLC bid RFP-098, RFP-100 as one bundled scope | pm-open-items.json
17 | ITB-019 | Exerplay | Sleeves are embedded by another sub four months before this sub installs | buy-out analysis
17 | ITB-019 | Exerplay | OPEN: 12 93 00 is claimed by both ITB-018 and ITB-019 | buy-out analysis
17 | ITB-019 | Exerplay | Exerplay carries four GMP lines across two packages — they must split cleanly | buy-out analysis
17 | ITB-019 | Exerplay | [HIGH] SPEC-C04 12 93 00 Site Furnishings — claimed by more than one scope doc | pm-open-items.json
17 | ITB-019 | Exerplay | [HIGH] SPEC-C05 32 91 13 Shot Put and Discus Mix — claimed by more than one scope doc | pm-open-items.json
17 | ITB-019 | Exerplay | [MEDIUM] BID-B05 Exerplay bid ITB-018, ITB-019, ITB-078 as one bundled scope | pm-open-items.json
17 | ITB-019 | Exerplay | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
18 | ITB-078 | YESCO | [MEDIUM] BID-B05 Exerplay bid ITB-018, ITB-019, ITB-078 as one bundled scope | pm-open-items.json
18 | ITB-078 | YESCO | [MEDIUM] BID-B09 YESCO bid ITB-072, ITB-078, ITB-089 as one bundled scope | pm-open-items.json
18 | ITB-078 | YESCO | [MEDIUM] GMP-06 Owner Accepted Alternates supersede drawn details | pm-open-items.json
19 | RFP-109 | Porta-King Building Systems | Manufactured building with no schedule activity of any kind | buy-out analysis
19 | RFP-109 | Porta-King Building Systems | [MEDIUM] SPEC-N04 RFP-109 holds no spec section of its own | pm-open-items.json
20 | RFP-021 | Elite Sports Builders | ZERO float — surfacing finishes the same day the field is contractually complete | buy-out analysis
20 | RFP-021 | Elite Sports Builders | Weather-dependent application in July at 6,000 ft | buy-out analysis
20 | RFP-021 | Elite Sports Builders | Only two real bidders; no recovery by rebidding | buy-out analysis
21 | ITB-054 | Crawford Door Sales of NV | [HIGH] GMP-02 Door 106 panic hardware exclusion is ambiguous | pm-open-items.json
21 | ITB-054 | Crawford Door Sales of NV | [MEDIUM] GMP-06 Owner Accepted Alternates supersede drawn details | pm-open-items.json
22 | RFP-060 | Jetstream Construction | One agreement, four exhibits (RFP-060, ITB-044, ITB-062, ITB-077) — none can issue until all four are drafted | buy-out analysis
22 | RFP-060 | Jetstream Construction | ITB-044 and ITB-062 are carried at $0; their money is inside RFP-060's $266,211 | buy-out analysis
22 | RFP-060 | Jetstream Construction | [HIGH] SPEC-C02 09 21 16 Gypsum Board Assemblies — claimed by more than one scope doc | pm-open-items.json
22 | RFP-060 | Jetstream Construction | [HIGH] SPEC-C03 10 26 00 Wall and Door Protection — claimed by more than one scope doc | pm-open-items.json
22 | RFP-060 | Jetstream Construction | [MEDIUM] BID-B03 Division 09 bid ITB-044, ITB-056, ITB-062, RFP-060 as one bundled scope | pm-open-items.json
23 | ITB-077 | Jetstream Construction | [HIGH] SPEC-C02 09 21 16 Gypsum Board Assemblies — claimed by more than one scope doc | pm-open-items.json
23 | ITB-077 | Jetstream Construction | [MEDIUM] SPEC-N03 ITB-077 holds no spec section of its own | pm-open-items.json
24 | ITB-044 | Jetstream Construction | [MEDIUM] BID-B03 Division 09 bid ITB-044, ITB-056, ITB-062, RFP-060 as one bundled scope | pm-open-items.json
24 | ITB-044 | Jetstream Construction | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
25 | ITB-062 | Jetstream Construction | [MEDIUM] BID-B03 Division 09 bid ITB-044, ITB-056, ITB-062, RFP-060 as one bundled scope | pm-open-items.json
25 | ITB-062 | Jetstream Construction | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
26 | ITB-085 | RESCO | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
27 | ITB-040 | Western Sealants | [MEDIUM] BID-B06 SI Legacy bid ITB-040, ITB-066, ITB-067 as one bundled scope | pm-open-items.json
27 | ITB-040 | Western Sealants | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
28 | ITB-074 | Henri | [HIGH] SPEC-C03 10 26 00 Wall and Door Protection — claimed by more than one scope doc | pm-open-items.json
29 | ITB-018 | Exerplay | [HIGH] SPEC-C04 12 93 00 Site Furnishings — claimed by more than one scope doc | pm-open-items.json
29 | ITB-018 | Exerplay | [MEDIUM] BID-B05 Exerplay bid ITB-018, ITB-019, ITB-078 as one bundled scope | pm-open-items.json
29 | ITB-018 | Exerplay | [MEDIUM] GMP-03 Trash receptacle exclusion vs the CFCI Site Equipment Matrix | pm-open-items.json
30 | ITB-072 | YESCO | [MEDIUM] BID-B09 YESCO bid ITB-072, ITB-078, ITB-089 as one bundled scope | pm-open-items.json
30 | ITB-072 | YESCO | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
31 | ITB-071 | ADP Lemco | [MEDIUM] GMP-04 Several ITB packages are unaddressed by the Basis of GMP | pm-open-items.json
32 | ITB-067 | Ryerson Concrete | [MEDIUM] BID-B06 SI Legacy bid ITB-040, ITB-066, ITB-067 as one bundled scope | pm-open-items.json
32 | ITB-067 | Ryerson Concrete | [MEDIUM] BID-B07 NRC bid ITB-066, ITB-067 as one bundled scope | pm-open-items.json
32 | ITB-067 | Ryerson Concrete | [MEDIUM] BID-B08 Ryerson bid ITB-066, ITB-067 as one bundled scope | pm-open-items.json
32 | ITB-067 | Ryerson Concrete | [MEDIUM] GMP-06 Owner Accepted Alternates supersede drawn details | pm-open-items.json
33 | ITB-070 | Cleaning Services Inc. | No scope narrative was ever issued — the exhibit is drafted from proposals | buy-out analysis
| ITB-066 | — | Scope removed by the Owner. No subcontract. | buy-out analysis
| ITB-066 | — | [MEDIUM] BID-B06 SI Legacy bid ITB-040, ITB-066, ITB-067 as one bundled scope | pm-open-items.json
| ITB-066 | — | [MEDIUM] BID-B07 NRC bid ITB-066, ITB-067 as one bundled scope | pm-open-items.json
| ITB-066 | — | [MEDIUM] BID-B08 Ryerson bid ITB-066, ITB-067 as one bundled scope | pm-open-items.json
| ITB-066 | — | [MEDIUM] SPEC-N02 ITB-066 holds no spec section of its own | pm-open-items.json

## basis
Generated | 2026-08-07
Sub + value authority | GMP R2 BackSheet (NCSD THS Field - GMP R2 - 070126.xlsm), rows 16-146. This is where the GMP's money actually lands. NOT the 05.12.26 bid tabulation, which is a transcription and is known to reverse RFP-008's two low rows.
Schedule authority | 05.7 Preliminary Construction Schedule (04.21.26), read at activity level, cross-checked against the 05.29.26 GMP schedule milestones.
Planned buy-out window | Schedule ID 19 'Procure Subcontractor Contracts', 5 d, Tue 7/21/26 – Mon 7/27/26. That window closed 11 days before this log was generated, with nothing issued. Every package therefore starts from a recovery position.
Ranking method | Backward pass, working days: latest release date = first field activity needing the sub − procurement − submittal review − submittal preparation − 15 d execution allowance (bonds, insurance, signatures). Rank is by that date, earliest first. Cost, delegated design, coordination and risk move a package up a tier and are recorded in 'Why This Rank' — they never create urgency the schedule does not support.
Duration basis 'sched' | The 04.21.26 schedule names that submittal, review or procurement activity and this is its own duration.
Duration basis 'judgment' | The schedule is silent for that package. The duration is a trade estimate and every one is also listed below as a schedule gap.
Execution allowance | 15 working days from issue-for-signature to executed, covering the subcontractor's signature, payment and performance bonds, and insurance certificates.
SCHEDULE GAPS FOUND | The 04.21.26 schedule has no submittal or procurement activity for ANY of the sports-field products, which is $3.1M of carried value: RFP-022 synthetic turf ($1,139,000), RFP-021 track surfacing ($450,741), RFP-023 fencing ($240,789), RFP-016 landscape & irrigation ($350,200), ITB-019 track & field equipment ($307,090), ITB-089 scoreboard ($99,483), RFP-109 ticket booth ($27,019). Their release dates below are computed from trade judgment.
STALE SCHEDULE LINES | The schedule still procures fire alarm (80 d) and fire sprinkler (20 d) material and submits drawings for both. Fire alarm is an express GMP Exclusion (08.04.26 ruling) and fire suppression is carried N/A at $0. Neither is a package and neither should stay on a procurement critical path.
ROLLED-UP LINES | Eight GMP lines are carried at $0 with a '(SEE LINE #xxx)' pointer and are bought inside another package: #004 building wrecking → 002; #009 utilities and #015 site signage → 008; #024 site concrete → 030; #026 site metals → 033; #049 metal panels → 045; #044 insulation and #062 acoustical ceilings → 060; #075 fire protection specialties → 074; #102 test & balance → 100; #107 sports field lighting → 103. They are shown on the log so none of them gets bought twice.
NOT IN THIS LOG | CORE self-perform and general conditions (GEN1 temporary construction requirements $57,630, GEN2 equipment $58,000, GEN3 waste management & cleaning $83,545, #104 temporary power & lighting $2,550), contingency, allowances, insurance and bonds. Per direction, this log covers the bid packages only.
ITB-066 | Fluid-Applied Flooring — scope removed by the Owner in a value engineering exercise (08.04.26). No subcontract will be issued. Those locations became sealed concrete under ITB-067.